## Slide 1: CRS Shelter Pilot update
August 8, 2019
SSNFI WG meeting – UNHCR

## Slide 2: Pilot Modality (UNHCR funds)
  Kiryandongo (4) and Kyangwali (2)
  CRS is procuring the hardware materials directly, provision of bricks is responsibility of the local crews engaged in the construction
  Payment is provided into 3 instalments: 40% for preliminaries, bricks supply and construction of walls up to the wall plate; 40% upon completion of roof, doors and windows; and 20% for finishes.
  Bidibidi (4)
  CRS is procuring the hardware materials directly for 4 shelters, provision of muddy bricks and labour is responsibility of the beneficiary with help of local leaders or proxy, crews engaged in the construction. One shelter is fully cash.
  Payment for muddy bricks and labour is provided into 2 instalments: 45% for preliminaries, bricks supply and 55% labour for completed shelter and latrine.
  Cash payment is in 3 instalments of 20% for brick supply and preliminaries, 60% for hardware materials and 20% labour for complete construction.

## Slide 3: Initial pricing – noting costs still being finalized
Shelter type | Shelter size (mxm2) | How many being built as part of UNHCR pilot? | Materials | Pilot Shelter cost (BoQ) USD | Pilot Latrine cost (BoQ) USD | Bathing shelter cost* (BoQ) USD | Pilot Total cost (BoQ) USD
One-room | 3,4m x 2,8m (ex) | 2 (Kir) | ISSB + CGI sheets | 907 | 300 |  | 1207
One-room | 3,4m x 2,8m (ex) | 1 (Kyangwali) | Mud bricks + CGI sheets | 572 | 300 |  | 872
Two-room | 4,55m x 3,3m (ex) | 2 (Kyan&Kir) | Mud bricks + CGI sheets | 704 | 300 |  | 1004
Three-room | 5,0m x 4,55m (ex) | 1 (Kir) | Mud bricks + CGI sheets | 810 | 300 |  | 1110
Two-room | 4.25m x 4m (ex) | 3 (Bidibidi) | Mud bricks + Aluzinc sheets | 572 |  | 125 | 697
 |  | 1 (Bidibidi) | Mud bricks + Aluzinc sheets | 572 | 254 |  | 825
Three-room | 5.0m x 4.0m (ex) | 1 (Bidibidi) | Mud bricks + Aluzinc sheets | 653 |  | 125 | 778
* Latrine without dome slab already built with support by other agencies

## Slide 4: ISSB – One-room shelter and latrine/bathing area in Kyangwali

## Slide 5: Mud brick – One-room shelters in Kiryandongo and Kyangwali

## Slide 6: Kyangwali – Roof being built first to prevent rain/wind damage

## Slide 7: Kiryandongo – Repairs to existing shelter considered