| Name | Litani TF | Meeting Date | 25 November 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 15:00 |
| Co-Chairs | Hussein Salem (MoSA) – Josep Zapater (UNHCR) | Meeting Duration | 2:00 hours |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |
| Purpose of Meeting | Review current Litani situation and agree on next steps |

Meeting

Discussions – Litani situation

MOIM explained that a few requirements for relocation have been requested by the Governor of the Bekaa, as per the below:

- A letter from MOIM to the Governor (already done),

- A letter from MOSA to the Governor, specifying the details of the camp to be relocated, including:

  - Current location,

  - Future location,

  - Number of Syrian Refugees and Lebanese citizens if any,

  - Number of tents,

  - Approval of neighbors of the relocation to the new land beside them.

- A letter from LRA confirming that the concerned camp or camps are those to be relocated for reasons of polluting the Litani river.

The following technical difficulties were tabled by WASH and Shelter sectors as regards relocation in winter time:

- Machinery will not be able to access relocation site for gravelling and improving, in case the ground is wet,

- Normally, families need to spend two to three days in the open while shelter assessment is done, materials are brought and tents are built. Winter conditions (cold and possible rain) are not adequate for current relocation modalities.

- New tents will not be firm upon wet ground – ground normally takes several days or even weeks to be up to standards for erecting tents, after a rain.

- Ground needs to be broken to install sanitation system, which is going to be 100% - which is not possible with wet ground.

During the subsequent discussion, it was agreed upon that necessary works need to commence without delay in the current sites, to prevent possible current pollution and in general improve WASH situation.

Action points – Litani situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| MOSA to consult neighbours | MOSA Bekaa | 27 November |  |
| MOSA to address letter with the specifications above | MOSA | ASAP |  |
| MOIM to explain to LRA difficulties related to relocation during winter | MOIM | ASAP |  |
| WASH and Shelter sectors to adapt current relocation plan to winter conditions, including secondary relocation in acceptable conditions | WASH and Shelter sectors – under UNHCR coordination (Raffaella) | ASAP |  |
| MOSA and UNHCR to re-start steps included in the meeting of 7th of October – including consultation with refugees. MOSA underlined that approvals need to be provided before the consultation, to ensure we keep credibility with concerned families. | MOSA and UNHCR | ASAP |  |

# Text boxes

Litani  TF – Draft minutes of meeting