## 2020 YTF plan
Youth Task Force Work Plan 2021
For all YTF activities, age, gender and disability should be taken into consideration
Indicator 1. | Number of professional humantarian workers attending the Compact workshop | [5 empty] | Baseline : 40 | Target : 60 (cumulative)
Indicator 2. | YTF Newsletter is issued | [5 empty] | Baseline : No | Target : Yes
Indicator 3. | IYD Celebration in Zaatari Camp | [5 empty] | Baseline : No | Target : Yes
Indicator 4. | Youth Commitee is activly engaged with YTF | [5 empty] | Baseline : No | Target : Yes
Objective | Activity | Sub-Activity | Q1 | Q2 | Q3 | Q4 | Responsible agency | Comments
Objective 1. Coordinate and promote information and resource sharing among key youth actors | Review YTF TORs | Chairs to Share ToRs with YTF members for revision by November 2021. The ToRs will be finalized by December 2021 |  |  |  | x | YTF Co-Chairs
| YTF Chairs Election | Chairs to share the call in March 2020 and the election to take place in April 2020 |  | X |  |  | YTF Co-Chairs | Election will take place in April 2021
| Knowledge Management | Coordinate with UNHCR on updating YTF information on Portal (Minutes, Fact sheets, and Newsletter) | x | x | x | x | YTF Co-Chairs UNHCR Coordination unit Amman
|  | Update Education/CP/GBV /Protection and Youth services map and contribute to 4 Ws of the Camp as needed |  | x |  | x | YTF Co- chairs all YTF members, and all relevant working groups and subworking groups.
|  | Update Services Advisor for all youth programming in Zaatari in collaboration with UNHCR Coordination Unit. | x | x | x | x | All YTF members, UNHCR Coordination Unit
|  | Translate the Service Advisor inputs to Arabic |  | x |  |  | YTF Co chair, UNHCR and Blumont
|  | Prepare and share an outline of trainings that can be provided by various agencies in Zaatari and share ad hoc trainings. | x | x | x | x | YTF Chairs and YTF members
|  | Coordinate with CMWG for dissemination of any messages needed. | x | x | x | x | YTF Chairs,Blumont, and UNHCR | Engage YTF Youth Commitee with CMWG
|  | Conduct Quarterly meetings with Education and Protection WG's to update on the workplan progress | x | x | x | x | YTF Co- Chairs and chairs of Protection and Education WG's + representatives from the youth commitee
|  | Coordinate with the youth commitee knowledge and information sharing | x | x | x | x | YTF Co-Chairs and Youth Commitee
|  | Coordinate a mapping meeting for YTF members to confirm 2021 projects and interventions and consult with the youth commitee for their feedback | X |  |  |  | YTF members + The Youth Commitee | YTF meeting in Feb 2021
| Monthly Meetings | Conduct YTF meetings on monthly basis | x | x | x | x | Co- Chairs
| Consultation on programme planning and assessments | Consultation on programme planning and assessments within YTF and youth stakeholders as well as with PWG, EWG, ADTF and other sectors as relevant. Organisations should present their intentions when designing new projects to make sure that gaps are taken into consideration and addressed. Approvals to be provided by ESWG and PSWG/CMWG for any projects involving community mobilisation. | x | x | x | x | YTF members , Youth Commitee with relevant actors as agreed
| Promote referrals between services | Encourage YTF members to implement referrals to and from youth related services between one another to benefit youth and build on their knowledge and skills. | x | x | x | x | YTF Chairs and UNHCR | This will be supported through the Services Advisor mapping. The services mapping to include information about organizations focal persons and contact details for easier referal
Objective 2: Improve responsiveness to youth needs in youth programming by developing youth strategies at the camp level, and develop capacity of youth, youth volunteers and field staff working with youth. | Youth Compact in Humantarian Settings Capacity Building | Conduct workshops on the Global Compact for young people in Humanitarian Action for members in all coordination stuctures in the camp including all WG's and TF's. The training to include engaging youth in COVID-19 Guidance |  | x | x |  | YTF Chairs
| 16 Days of Activisim joint YTF event |  |  |  |  | x | All YTF members in coordination with Protection and SGBV WG's.
| Support coordination structures in improving their programming and messaging targeting youth | Conduct adolecnsts and youth situational analysis | x | x |  |  |  | Support a camp focused youth and adolescnts situational assessment to identify key areas of interventions. In case the assessment was not supported YTF Chairs and members can lead FGDs with overall youth concerned issues
|  | Conduct joint meetings with identified working groups and agree on road maps for joint interventions |  | x | x | x |  | This can be an extension of SGBV focus on harassment and cyver harassment + Liveilhoos focus + the emerging focus on MHPSS
|  | Provide support for WG's in developing youth friendly messages and provide guidance on approaching youth in the camp | x | x | x | x | Chairs and FP's from YTF members to respective working groups.
|  | Support Chairs of Working groups in the camp to create youth committees for their working groups. This is upon request from Chairs |  |  |  |  | Cahirs and YTF members involved in the commitee
| Enhance engament of young people with disabilities | Coordinate with ADTF the technical capacity building for YTF members and Youth educators for engagment and service provision for PWD |  |  |  |  | YTF + ADTF
|  | ADTF to assess YTF service mapping and identify key areas of improvment for youth services in the camp to better engage PWD |  |  |  |  | YTF + ADTF
Objective 3. Advocate with Donors, implementing agencies, camp and national authorities and advocacy groups for the needs of youth in the camp and for the implementation of activities that respond to those needs through the PSWG and ESWG. | YTF Newsletter | Compile existing information on programming, coverage and best practices (with a newsletter) |  | x |  | x | YTF Chairs to compile and contributions from all YTF members + The Youth Commitee to lead the development of a newsletter
| YTF Fact sheet | Develop a Fact sheet that includes useful information on youth services in Zaatari camp for 2021 |  | x |  | x | YTF chairs | Utlized the inputs from the youth assessment
| Advocacy events and messaging | Collaborate with all coordination groups in the camp to ensure youth are integrated into sector advocacy strategy and share advocacy message summaries by activating the FP's system among coordination structures in the camp | x | x | x | x | Chairs and assigned FP's to different working groups and the Chairs of WG's in the camp level | Include standing agenda point on YTF updates of YTF & other sector meetings
|  | Use advocacy messages from YTF engagment with youth through the YTF Youth Commitee and promote them in joint events such as IYD, 16 Days campagin, and reflect them in newsletters and any communication with sectors, with donors and decision makers and review in Q3 for revision as needed. | x | x | x | X | All YTF members respectively | These summaries should be shared with ESWG and PSWG as well on a quarterly basis. In coordination with Amman level Advocacy Group. At Zaaatri level UNHCR external relations will provide support . (best practices, capacity support and youth led projects, work opportunities, and issues related to education, increased opportunities to volunteer, Advocate for more places for youth in the camp and more opportunities for them to access centers for courses (including transportation support and coordination between existing activities to avoid timing conflicts, Advocate for more diverse and relevant accredited learning and training programmes). Notes: *accreditation of NGO programmes *outreach through home visits- YTF support *establishing a program for youth as volunteers with no needed previous experience *ease the process for employed youth to continue study. *advocate for more outside camp training opportunities.
| International Youth Day | International Youth Day celebration |  |  | x |  | All YTF members respectively | Ensure diverse young people engagment "gender, age, disability..etc"
Objective 4. Promote youth participation in programme planning, setup and implementation, both in youth and non-youth specific programme responses. | Support the YTF Youth Commitee | Review TORs and roles and responsibilities |  |  | x |  | co-chairs and YTF members | Evaluate the process and document it.
|  | Provide capacity building for selected youth and connect youth commitee members with available opportunities | x | x | x | x | YTF member organizations
|  | Arrange regular meetings between YTF members and the YTF Youth Commitee | x | x | x | x | RI with the support of YTF members | Encourging youth to participate in the development of programs based on their needs and aspirations. Identifying techinques to reach out for youth in order to discuss their needs through regular meetings. Individual and group home visits for youth with disabilities. Activating youth initiatives that ensure gender balance and inclusion of youth with disabilities within their communities.
| Promote Youth Innovation in the camp | Coordinate between YTF and UNHCR Innovation Lab to support youth led solutions for identified challanges in the camp by youth |  |  | x |  | YTF + UNHCR Innovation Lab | With a focus on young women and girls
| Promote youth participation in the camp | Promote the participation of youth, using their capacities and knowledge to develop and initiate community activities to respond to needs and gaps identified. This would include integration of youth as actors in data collection and research on relevant youth issues taking into consideration of age and disability and including YWD and vulnerable youth. | x | x | x | x | All YTF members + Youth Commitee | 1.Youth engaged in joint planned events such asIYD, 16 Days ...etc 2.Encourage youth to implement initiatives/civic engagement projects at community level. 3. Motivate Youth by reawarding them 4. Youth are engaged in YTF planning meetings

## Sheet3
Conduct joint meeting with SGBV WG on common areas of interest and coordinate with SGBV SWG on training for YTFmembers on referrals around GBV. | x | x | UNFPA