## IS-coordination
2022 LCRP Sector Workplan - Sector Coordination / Inter-Sector priorities
2022 Timeline
Link to IS Priority/Mainstreaming Area Or link to IS priority | Key Priorities | Main actions | Q1 | Q2 | Q3 | Q4 | Responsible/main partners involved
IS Joint Priority 1: Joint Analysis | Defining and understanding needs and targets through annual vulnerability assessments | Revision of VASyR analysis plan and questionnaire |  | X |  |  | BA Sector Coordinator, BA Core Group,
|  | Presentation of VASyR results and identifying needs for BA Sector |  |  |  | X | WFP, UNHCR. VASyR Core Group, Inter-Agency IM
|  | Exploring findings from up-coming assessments on Lebanese and defining needs and targets of vulnerable Lebanese | X | X |  |  | BA Core & Working groups with support from IM and inter-secter teams
| Ensuring that the Expenditure Baskets used to estimate poverty and calculation transfer values for MPCA are updated with the latest data and reviewed to reflect needs of the targeted population | Initial review of the SMEB components and methodology including methods used to calculate transfer values |  | X |  |  | BA Core Group in collaboration with FSA
|  | Update/Revision of the SMEB with latest data from VASyR |  |  | X
|  | Monitoring the value of Survival Minimum Expenditure Basket with new price data | X | X | X | X | WFP, BA Sector Coodinator (Non-food services)
Coordination | Ensure linkages with national systems and national social protection strategies | Set up system and methods for tracking assistance to Lebanese including understanding the degree of overlap between different programs. | X | X |  |  | BA Sector Coordinator, key partners, BA Field Coordinators
|  | Set up methods by which partner assessments can feed in to NPTP database and/or other social safety net/social protection interventions |  | X | X |  | BA Sector Coordinator
| Ensure all IM tools and dashboards are up to date to allow for efficient access and use | Keep the service mapping updated and available to target population and partners | X | X | X | X | BA Sector Coordinator, BA IM focal point
|  | Ensure monthly updates of the S/MEB dashboard | X | X | X | X
|  | Ensure timebound reporting on Activity Info and direct update of reporting dashboard | X | X | X | X
| Ensuring linkages with other response frameworks and cross cutting themes | Involvement in the cash working group and relevant structures. | X | X | X | X | BA Sector Coordinator, BA Core Group
|  | Ensure cross attendance and participation in the other sector's working groups and provide important sector updates. | X | X | X | X
|  | Maintain coordination and communication with other coordination platforms (ERP- FS and BN) | X | X | X | X
| Advocacy | Discussions around transfer values for multi-purpose cash assistance within the Core Group and the Basic assistance working group | X | X | X | X | BA Sector Coordinator, BA Core Group
|  | Continuous monitoring of key socio-economic indicators (exchange rate and consumer price index) | X | X | X | X | BA Sector Coordinator
| Development of Sector Level guidance documents and compliations of lesson learnt linked to specific topics | Develop guidance notes/SOPs for multipurpose cash assistance covering intended impact, targeting mechanisms, defining transfer values, referrals and reporting | X |  |  |  | BA Sector Coordinator, BA Core Group
|  | Develop lessons learned/best practices on cash modalities for MPCA |  | X |  |  | BA Sector Coordinator, BA Core Group; potential collaboration with FS&A Sector
Reporting, Monitoring and Evaluation | Provide partners with resources for robust M&E of BA programs while streamlining core sector indicators across the response | Update M&E tools and guidance for post distribution monitoring and outcome monitoring, including the development of a reference sheet for Core BA Indicators | X |  |  |  | BA M&E taskforce
|  | AAP: Define sources for beneficiary feedback through partners and develop a common resource pool with Quarterly/bi annual review of available beneficiary feedback to feed into Sector level discussions on the topic |  | X | X | X | BA M&E taskforce
|  | Keep ActivityInfo reporting updated | X | X | X | X | BA Sector Coordinator and IM
|  | Keep the Inter-Sector service mapping updated | X | X | X | X
|  | Produce quarterly reporting dashboards | X | X | X | X
|  | Update the interactive dashboards | X | X | X | X
|  | Review and update of Research Questions to the Inter-Sector |  | X |  |  | BA Core Group, M&E taskforce
Mainstreaming- Protection | Review Protection Risk Assessment (PRA) | Define priority risks, including SGBV Risk analysis in cooperation with GBV Risk Mitigation Committee (SGBV TF) |  | X |  |  | BA Sector Coordinator, BA Field Coordinators, support from Protection Sector
|  | Define mitigation measures and monitoring plan for prioritized risk and begin implementation |  | X | X
|  | Review of risks with partners for strategy planning |  |  |  | X
Mainstreaming- Prevention of Sexual Exploitation and Abuse | Ensuring complaints and feedback mechanisms (CFM) provide access to safe, accessible reporting for sexual exploitation and abuse (SEA) | Set up BA PSEA taskforce and develop PSEA training package | X | X |  |  | Sector PSEA focal points, BA Sector Coordinators
|  | Bilateral discussions with partners who do not have PSEA or CfMs systems in place to understand needed support | X | X
|  | Conduct a training of trainers for BA partners |  | X
|  | Develop guidance notes for partners: HR guidance note and guidance on risk analysis. |  | X | X
Mainstreaming- Conflict Sensitivity | Engage with Conflict Sensitivity Mainstreaming FP to ensure cash implementation is carried out with a conflict sensitive approach | Quarterly updates on the Tensions Landscape at BA Working Groups/ Training of Partners on CS | X | X | X | X | BA Sector Coordinator, Conflict Sensitivity Mainstreaming FP, Social Stability Sector Coordinator
|  | Thematic discussions with Conflict Sensitivity focal point |  | X | X | X
Mainstreaming- Gender and SGBV | Ensure recommendations from Sector Focal points are implemented | Trainings on practical implementation aspects of SGBV risk mitigation for partners under the sector |  | X |  |  | Sector GBV focal points, BA Sector Coordinator
|  | Gender in Humanitarian action training is conducted in 2022 at national and regional level |  | X | X | X | Coordinator and Gender Specialist
|  | Gender analysis two pager is drafted with support from Inter-Agency Gender Specialist |  | X |  |  | Gender/SGBV FP, Coordinator and Gender Specialist
|  | Nomination of gender and SGBV Focal point of the sector | X |  |  |  | Gender/SGBV FP and Coordinator
|  | Start a reflection on how to ensure that distribution/cash cards can include both wife and husband or be in the name of women |  |  | X |  | Coordinator and Gender Specialist
|  | Analyse disaggregated sector results on a quarterly basis and adapt activities to address gender inequalities if relevent | X | X | X | X | Coordinator and Gender Specialist
|  | Mapping of women's organisations and meeting on how to engage with them to strenghten assessents and delivery |  |  | X |  | Coordinator and Gender Specialist
Note on A23: marius birsan: We inserted Reporting activities, same for all sectors

## Logframe Activities
2022 LCRP BA Sector Workplan - Log frame Activities
2022 Timeline
Sector Output | Key Activities | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Additional Comments | Statuts
Outcome 1: Strengthen the ability of vulnerable households and individuals, including female-headed HHs, persons with disabilities and children, to meet their basic survival needs
Output 1.1: Poor and vulnerable households and individuals benefit from unconditional, unrestricted cash assistance grants | Activity 1: Revise and update formula for targeting Displaced Syrians, including household level profiling |  | X | X | X | UNHCR, WFP | UNHCR, WFP | In collaboration with FS&A Sector
| Activity 2. Develop guidance for targeting Lebanese host communities and streamline efforts for harmonized methodologies within the sector | X | X |  |  | BA Sector Coordinator, BA Core Group | Partners with on-going BA programs to Lebanese
| Activity 3. Provide multi-purpose cash transfers to the most economically vulnerable to support their survival needs | X | X | x | X | Partners with on-going BA programs | Partners with on-going BA programs
| Activity 3. provide social grants to groups of households facing specific lifecycle vulnreabilities (i.e. child grants, disability grants, social pension) | X | X | X | X | UNICEF, ILO, GoL, CSOs, Save | MOSA, UNICEF, ILO
| Activity 4. Present research and increase learning opportunities on social assistance programming | X | X | X | X | BA Sector Coordinator
| Activity 5. Thematic trainings for partner staff (communications with communities, safe identification of protection risks and referrals, social safety nets and social protection |  | X | X |  | BA Sector Coordinator, PSEA, GBV and Social Stability focal points
| Activity 6. On-going review of the Protection Risk Analysis Matrix and minimum standards for protection mainstreaming and accountability |  | X |  |  | BA Core Group |  | With support from the protection sector
| Activity 7: Development of post-distribution and outcome monitoring Sector level tools and guidance | X |  |  |  | BA M&E Taskforce
| Activity 8: Monthly review of expenditure baskets and transfer value recommendations, including assessment of available services intended to be covered through the SMEB | X | X | X | X | BA Core Group
Outcome 2: Strengthen the ability of populations affected by seasonal hazards and emergencies to secure additional basic survival needs
Output 2.1. Population affected by seasonal hazards and emergencies benefits from cash grants. | Activity 1: Identification and verification of eligible households |  |  | X |  | BA Coordinators (National and regional), Partners with planned winter cash programs
| Activity 2: Distribute cash assistance to households highly vulnerable to seasonal/winter shocks | X |  |  | X | Partnes with planned winter activities
| Activity 3: Incorporate indicators in to monitoring tools and guidance at sector level |  |  | X |  | M&E Taskforce
| Activity 4: Yearly review of the Winter Cash assistance Sector guidance note |  |  | X |  | BA Coordinators (National and regional), BA Core Group
| Activity 5: Develop guidance for targeting Lebanese host communities and streamline efforts for harmonized methodologies within the sector |  |  | X | X | BA Sector Coordinators (National and regional), BA Core Group | Partners with on planned BA winter programs to Lebanese
Output 2.2: Population affected by seasonal hazards and emergencies benefits from in-kind assistance | Activity 1: Identification and verification of eligible households, including guidance note on In-kind distribution (eligibility, targeting, item selection, etc.) | X | X | X | X | BA Coordinators (National and regional), Partners with planned in-kind response | UNHCR | Inclusion of women and girls in item selection
| Activity 2: Distribution of in-kind assistance to households highly vulnerable to seasonal/winter shocks | X |  |  | X | BA Coordinators (National and regional), Partners with planned in-kind response
| Activity 3: Provide in-kind assistance for populations affected by emergencies | X | X | X | X | BA Coordinators (National and regional), Partners with planned in-kind response
| Activity 4: Review core relief item contingency in-kind stock |  |  | X | X | BA Coordinators (National and regional), IM, Inter-Sector team | UNHCR | As part of the the Inter-Sector contingency stock review
Outcome 3: Effective and efficient service delivery through strengthened linkages with national social safety net programmes and social protection systems
Output 3.1 Linkages between partners supporting vulnerable and extreme poor Lebanese are strengthened | Activity 1: Conduct workshop with NPTP and NGO partners around needs assessment to extreme poor Lebanese | X |  |  |  | BA Coordinators, BA Core Group, NPTP counterparts | WFP
| Activity 2: Provide regular updates and briefings on the NPTP to sector partners at the national and field level | X | X | X | X | BA Coordinators, NPTP counterparts | MoSA, WFP
| Activity 3: Set up system and methods for tracking assistance within and outside the NPTP | X | X |  |  | BA Coordinators, partners with on-going BA programs to Lebanese | MoSA, WFP
| Activity 4: Set up methods by which partner assessment can feed in to national unified registry |  | X |  |  | BA Coordinators, partners with on-going BA programs to Lebanese, NPTP counterparts
Output 3.2 Strategy developed for coordination and alignment between humanitarian assistance and different social assistance interventions as part of a national social assistance system and social protection strategy | Activity 1: Draft roadmap for coordination and alignment through multi-stakeholder discussions |  | X | X |  | BA Core and Working Group | UNHCR, UNICEF, SCI, | In coordination with National Social Protection Strategy
| Activity 2: Documentation of best practices of existing cooperation of humanitarian assistance and national social assistance systems and social protection strategies |  | X | X |  | BA Core and Working Group | UNHCR, UNICEF, SCI