## Workplan
Romania MHPSS sWG: Emergency Response Plan
General Actions | Specific Actions | By? | When | 1st Week July | 2nd Week July | 3rd Week July | 4th Week July | 1st Week August | 2nd Week August | 3rd Week August | 4th Week August | 1st Week September | 2nd Week September | 3rd Week September | 4th Week September | 1st week of October | 2nd week of October | 3rd week of October | 4th week of October | 1st week of November | 2nd week of November | 3rd week of November | 4th week of November | 1st week of December | 2nd week of December | 3rd week of December | 4th week of December | Status | Notes
1. Provide a technical platform for better coordinated and focused inter-agency emergency response to the MHPSS needs of populations of concern in Romania
Coordinate programs, activities and plans through regular sub Working Group meetings |  | WHO | Friday 1:30 PM (bi-weekly) | [24 empty] | Ongoing
Develop/ update MHPSS Service Mapping periodically to understand the availability of MHPSS services (needs, gaps, coverage), and to aid with referrals. |  | WHO | 2022-05-01 | [24 empty] | Planned
Update Emergency Response Plan to follow up with the progress of action |  | WHO | Friday 1:30 PM (bi-weekly) | [24 empty] | Ongoing
Provide input to policies and plans as required, including referral systems, standard operating procedures, advocacy and resource mobilization
2. Strengthen the safe and ethical service provision aligned with IASC standards, analysis and transparent sharing of data and information pertaining to MHPSS needs, priorities and activities in Romania, including needs assessments
Ensure the sharing of assessment results within the group, provide technical support for the development of the assessment tools, and coordinate joint assessments |  | SCI UNHCR UNICEF | 2022-04-01 | [24 empty] | Ongoing
Create an accessible, user friendly, effective, and functional online platform to share and disseminate MHPSS reports, tools, documents, materials and lessons learned developed by member agencies |  | WHO | 2022-03-01 | [24 empty] | Done | https://worldhealthorg-my.sharepoint.com/:f:/g/personal/apaydinm_who_int/EhiSLNq6bJVLvOIYBXVepbgBTWjh9qRkDOa7cSyW4dv-1Q?e=zrnDmg
Encourage members to report on their MHPSS activities, staff capacities, achievements, and challenges in monthly basis to the MHPSS Task Force | Reporting Template to be developed | WHO | 2022-04-01 | [24 empty] | Planned
Coordination for service provision focused on vulnurable groups |  | Mozaiq LGBTI MoH Estuar MdM | 2022-04-01 | [24 empty] | Ongoing
Coordination for the list of MHPSS professionals who speaks UKR/RUS language in Romania |  | MoH ICAR | 2022-04-01 | [24 empty] | Done | List of MHPSS Professionals UKR-RUS
Coordination for referrals |  | GBV/CP/Protection | 2022-04-01 | [24 empty] | Ongoing
Coordination for IEC materials on available MHPSS services |  | WHO-MoH Ionut | 2022-04-01 | [24 empty] | Done | Check One Drive
Coordination MHPSS Hotline for people coming from UKR / frontline worker / volunteers | Establishment for Telehealth system | MoH Mozaiq LGBTI Estuar | 2022-04-01 | [24 empty] | Done | List
3. Promote and support for quality MHPSS interventions through joint capacity building activities to ensure quality standards
Organizing webinars and workshop on MHPSS in Emergency Settings |  | WHO/IOM/UNICEF/MSF/UNHCR (for webinars, NGOs and Government) | Wednesday 10 AM (Workshops) | [24 empty] | Ongoing | CB MHPSS in Emergency Settings Child/Adolescent Focused MHPSS 4Ws Specialized Services in Emergency Settings Scalable MHPSS Interventions
Develop a capacity building plan based on interagency capacity assessments and organise training workshops to build the technical and institutional capacity of humanitarian agencies and government institutions (workshops, seminars, conferences, training sessions) |  | WHO | 2022-04-01 | [24 empty] | Not started | IASC MHPSS Webinar PFA Webinar
To mainstream MHPSS into other sectors so that it is an integrated part of the overall humanitarian response. | [27 empty] | Not started
Follow up the translation of the MHPSS guidelines into local language | Importance of MoH capacity | WHO UNICEF | 2022-04-01 | [24 empty] | Ongoing | WHO is translation 4W and RG Assessment Guideline
Coordination for PFA Capacity Building Interventions |  | MoH SCI ESTUAR War Child | 2022-04-01 | [24 empty] | Ongoing
Coordination for interpreters/translation capacity
Coordination for Self Care / Staff Care (especially for volunteers) |  | Adam Lacey MoH- Estuar | 2022-04-01 | [24 empty] | Not started
4. Promote the engagement and leadership of the government and encourage the representation of diverse MHPSS partners and stakeholders within the TF, including government partners, UN agencies, I/NGOs
Maintain communication with focal points and ministries, encouraging their active involvement |  | Dr Gabriel Diaconu | 2022-04-01 | [24 empty] | Done
Align the Task Force objectives and activities with national Mental Health Strategy |  | WHO - MoH | 2022-05-01 | [24 empty] | Planned
Support national health pllan regarding mental health |  |  | 2022-05-01 | [24 empty] | Not started
Publish periodic situation reports of MHPSS WG with humanitarian response web site, OCHA, MHPSS RG | Reporting Template to be developed | WHO | 2022-04-01
Create a bridge between international donors and NGOs to establish partnership opportunities for MHPSS projects | [27 empty] | Not started