Nutrition Working Group Jordan 6th November 2012  Meeting Minutes and Action Points

Attendees: Shannon Patty (WFP), Ola Sharif (IMC), Carine Morel-Boyce (UNICEF), Buthyana Al-Katib (UNICEF), Ann Burton (UNHCR),Rasha Alzein, Kym Blechyden Richard Casagrande (SCF)

- Discussion  of UNHCR Snr Nutriton Advisor Mission report and recommendations

| Recommendations | Discussion and Actions to be taken | By Whom |
| --- | --- | --- |
| 1. Nutritional surveillance |  |  |
| UNHCR should ensure that all clinics ( Za’atri and refugee receiving clinics outside) are adequately equipped with anthropometric equipment Approach UNICEF to see if current survey equipment can be donated. | - IAHK contain MUAC tapes scales and height boards. Seven kits recently received and will go to JHAS - Decide on number of clinics to be equipped - UNICEF and WHO to follow up with MoH re their clinics and need for anthro equipment - UNHCR to procure additional stock to meet gap which UNICEF cannot provide | None UNHCR UNICEF/WHO UNHCR |
| Newly arrived children to Za’atri camp should be systematically measured upon arrival. | - Review current screening arrangements and discuss with JHAS re possibility of MUAC screening - Provide MUAC tapes, training and screening criteria | UNHCR (immediate) in consultation with Nutr WG |
| Establish screening for children at clinics - MUAC taken on all children and then - If MUAC is < 135mm the child is weighed and measured OR children should be weighed and measured upon clinical signs of wasting | Discussion of different approaches. Possibilities: 1. MUAC of all children being immunized (but stops at 18 months ). 2. Growth monitoring but which target group? 2. Screening all children under 5 on arrival at clinic. Need to identify mother’s preference for nutrition screening No consensus reached other than for new arrivals - Wait for results of survey to see prevalence of malnutrition | Nutrition working group in consultation with health partners after survey results known |
| Train health staff in the correct procedures for the measurement of weight, height, MUAC and detection of oedema | Follow up with different depts in MoH (MCH, IMCI ) or American University of Beirut | UNICEF |
| 2. CMAM capacity |  |  |
| Decide on the necessity of setting up a very small CMAM capacity in the camp and in the clinics out of camp that receive Syrian refugees. | Discussion: no protocols nationally for CMAM. Children with severe malnutrition admitted. Need approval for RUTF and supplemental products. Best to look for local options. - Await results of nutrition survey to estimate numbers of cases and decide next steps with MoH. - Children identified now should be referred to hospitals | Nutrition working group |
| 3. Nutrition survey |  |  |
| Share the raw data and the preliminary report for review with UNHCR HQ for validation |  | UNICEF (end November) |
| 4. IYCF |  |  |
| Provision of fortified porridge for children 6 – 23 months For priority action. Locally procured iron and other micronutrient fortified porridge (preferably also containing milk) be procured for distribution for children 6 – 23 months residing in Za’atri camp | UNHCR waiting results of tender to determine availability of budget. Distribution mechanisms discussed ? through WFP but not part of general distribution - Calculate quantities and estimated cost and procure if funds available - Need to do taste test before procuring - Develop Sensitisation plan - Need to decide on distribution mechanism if goes ahead | UNHCR WFP Nutrition Working group Nutrition Working group |
| Discuss with WFP should be held to see whether supercereal plus (CSB++) could be provided to this caseload until such time as refugees in the camp have access to fortified porridge or fresh foods suitable for complementary feeding of young children. | Supercereal has long lead time to procure and now going to vouchers soon. Timeline - UNICEF has emergency 8 day supply time - WFP needs a 3 month period for supplies to arrive, but waiting on results of Nut Assess. - UNHCR states it’s WFP’s role to provide supplementary food for malnutrition management (Global MoU) - Pregnant and Lactating Women - Why are we not covering? - Wait for results of nutrition survey |  |
| Management of Infant Formula and feeding equipment - Needs and Donations Continue under medical prescription and control, required quantities of formula milk for infants that really need it (under JHAS only in the camp) Create strong linkages between the Save-the-Children baby tent programme and the JHAS for referral of patients in difficulty in both directions and to ensure consistent messaging. SOPs to be developed on the management of donations of infant formula, feeding equipment and other breast milk substitutes and an organization nominated to manage this. | Much as already been done but needs go be constantly monitored. - SCF to position staff at clinic to monitor - Strengthen capacity of service providers to manage breastfeeding problems - Work with community groups to make sure aware of concerns re BMS and use Syrian community mobilizers - Share statement already signed by agencies in camps - Develop guidance on management of donations based on Lebanon experience if not already covered - Try and obtain letter from MOH at the central level | SCF SCF SCF WFP UNHCR with NWG UNICEF/WHO with NWG |
| ## 5. Anaemia and Micronutrient Deficiencies |  |  |
| Equip centres with rapid diagnostic tests – hemocue 301+ machines, 301+ micro cuvettes and safety lancets and associated equipment |  | UNHCR (immediate) |
| Test children <5 and PLW systematically and fu according to the national protocols. | Establish screening and management protocols | UNHCR and Nutrition working group with health agencies |
| Ensure that refugees also have access to the various elements of the national nutrition programme both inside and outside of the camp. | Refugees part of national programmes e.g. salt iodization, fortified bread, school feeding program (poverty areas) |  |
| Explore possibility with SC-Jordan to extend their anaemia control programme to refugee areas and to the camp. | SCF programme in 4 parts of country targets children <5 and WRA; screening with haemacue, awareness, Fe treatment and supplements and follow up Hb. Has been shown to improve Hb levels | UNHCR and Nutrition working group |
| 6. Food assistance |  |  |
| Until the voucher system is installed in the Za’atri camp add in a vitamin C rich product in the complementary food basket e.g. timed tomatoes (not tomato paste) | According to WFP already receiving tinned tomatoes. Apparently ration has changed. - Share current complementary ration with WFP - Calculate current nutval | UNHCR WFP |
| Finalize plans for the voucher system in the camp so that refugees are able to have access to a variety of fresh foods to supplement their diets. | Need update on timeline | WFP |
| Advocate for market opportunities within the camp so that refugees have access to a greater range of fresh foods. | Part of voucher preparation |  |
| 7. Capacity Building |  |  |
| - UNHCR Jordan need to explore how much budget could be allocated to a training by IMC and AUB as well as more ongoing training in Breastfeeding from national breastfeeding associations in collaboration with Save the Children and JHAs | UNHCR to fund IMC to conduct training n nutrition in emergencies for Jordan agencies involvedin Syrian response IMC training targeting staff working w/ refugees, in Arabic Dec 15-19th Send invitation, look for staff Jordanian breastfeeding associations not discussed. Next meeting | IMC |

- Nutrition survey data collection started in Za’atri on the 3rd of November.  Going slower than expected because of difficulty finding  tents.  Expect preliminary results mid-November.  Initial findings indicate malnutrition not  a public health problem i.e.  GAM less than 5%

- Save the Children activities

  - Surveillance of newborn health, breastfeeding initiation, anemia

  - Baby Tent Program

    - Targeting Children under 5, women in reproductive age, pregnant and Lactating Women

    - Tent to tent follow up

  - Staff targeting women in waiting area of JHAS clinic

- Communication strategy Focus group Thursday  will include breastfeeding and camp setting challenges

- AOB Mainstream talk of urban refugees

- Meeting schedule- every 2nd Tuesday at 10.  Next meeting November 20th @ UNICEF