Minutes of Meeting

Nutrition Sub-working group

Date:August 12, 2014 @ 9:00 AM

Location:WFP, Beirut - Downtown

- List of Participants

| Names | Organization | Email |
| --- | --- | --- |
| Juliette Seguin | ACF | jseguin@lb.acfspain.org |
| Dima Ousta | IOCC | dousta@iocc.org |
| RabhaCharafEddine | MoPH | Rabha.zreik@gmail.com |
| Malak Rahal | UNHCR | rahal@unhcr.org |
| Rima Shaya Ghraizi | MOPH | rgs066@gmail.com |
| Edwina Zoghbi | WHO | zoghbie@who.int |
| Soha Moussa | WFP | Soha.moussa@wfp.org |
| Catherine Said | WFP | catherine.saiid@wfp.org |
| Najwa Rizkallah | UNICEF | nrizkallah@unicef.org |
| Suzanne Mboya | UNICEF/MENARO | suzannemboya@outlook.com |
| Maya Assaad | MoPH | Maya_m_assaad@yahoo.com |
| WafaaHoumani | MoPH | Wafaa.houmani@hotmail.com |
| Ali Ghassani | MSF Swiss | Msfch_lebanon_DMedCo@geneva.msf.com |

- Proceedings

| Discussion Points |  | Action Point |
| --- | --- | --- |
| Strategy Work plan/ action plan | - IOCC, WFP, UNICEF and MoPH PHC Department met with new Nutrition Unit at MoPHto introduce current projects in Lebanon and discuss/suggestworkplanof the new Nutrition Unit. - Setting vision for upcoming 3 years, national protocol on nutrition in emergencies, growth monitoring, IYCF/IYCF-E, incorporating NIE in curricula etc. The vision and projects are to be put according to the decree. - Copy of the decree of the new Nutrition Unit was shared at the meeting - Further discussions will be held once matrix of activities is filled out. | - IOCC to send matrix for amendments, trial and finalization - WFP will incorporate the current nutrition activities to the different sections in the decreeof the Nutrition Unit |
| Mass screening campaign | - Mass screening campaign results were presented by UNICEF, Ms. Najwa Rizkallah. - Target number of children to be reached was 16,785 (assuming 20% from the total number of registered refugees in ITS in Bekaa) - 16,531 children were reached (52% male, 48% female) - 828 children identified as MAM, SAM, or with MUAC between 12.5 to 13.5 were given referral to PHC - 518 children came to the PHCs: 432 of them had been given referral and 86 without referral (were called upon) - 77 were confirmed as MAM at PHC and 25 were confirmed as SAM. - At the community level: 152 were identified as MAM and 135 as SAM. - Discussion on PHC versus field identification and MUAC versus weight/height as tools for identification of malnutrition; these topics could feature in 2 separate publications. - Z-scores of children referred to the PHCs reflect a normal distribution which suggests that currently there is no malnutrition crisis. - Data from the screening campaign suggested that 25% of children were not vaccinated for Polio. - IYCF data from campaign suggests that 48% of women were exclusively breastfeeding children at 1 month of age, 36% at 2 months and 28% at 4 months. | - Dr. Najwa will share presentation |
| Establishment of technical committee | - Technical committee not yet formed. MoPH suggested Dr. Lamis Jomaa and Dr. Maha Hoteit to be part of the technical committee. - Dr. Najwa from UNICEF suggested that Ms. Sabeen Abdulsater could be part of the technical committee since Najwa will be leaving Lebanon by end of August. |  |
| Growth monitoring | - 100,000 copies are being printed by MoPH. |  |
| IYCF-E | - Dr. Suzanne Mboya, Regional Roving IYCF-E Specialist, UNICEF consultant, attended the meeting. - Presentation by Danone-Nutricia (see AOBs) - No new action points. |  |
| Micronutrient distribution | - SOP on the distribution of micronutrients is pending technical committee decision. | - Technical committee to work on SOP for micronutrients. |
| AOB | - MoPH/WHO providing supplying weight scales and height boards to PHCs. IOCC to share list of activated centers with WHO as these centers have already received these supplies from UNICEF. - UNICEF is running short on Plumpynut and Plumpysup. - IOCC has a stock of Sprinkles that will expire end of September. Suggestion of blanket distribution of Sprinkles in school sites and communities (not just PHCs). IOCC to provide sample to MoPH. - Nutrition matrix was presented and discussed during meeting. IOCC to share matrix with NSWG to be filled out. - Presentation by Danone-Nutricia: company interested in promoting healthy nutrition and best start in life as part of the company’s CSR. Topics of interest to the company: education on fruits & vegetables, childhood obesity, importance of breastfeeding, importance of adapted milk. - Company met with MoPH (Ms. Pamela Zgheib) for incorporation of nutrition messages in the “child registry” books – carnet de santé. - Company interested in collaborating with paediatricians and nurses on nutrition education programs in nurseries - Company interested in launching nutrition education through doctors using “Nutricheck” as a tool that the latter can administer to mothers to assess the adequacy of their children’s diet - NSWG informed Danone-Nutricia that despite the good suggested activities, it is not possible to collaborate with them at this time given the multiple and current violations of the Code on BMS as this constitutes conflict of interest; members of the NSWG have noted that artificial milk (e.g. Aptamil) is being distributed for free to women who are giving birth in hospitals, as well as through paediatricians in clinics. NSWG suggested collaborating with Danone-Nutricia on addressing violations of the Code in Lebanon. |  |
|  | Next meeting: September 9, 2014 at 9.00 AM at WFP |  |