|  | Meeting |  |  |  |
| --- | --- | --- | --- | --- |
| Name | Assessment WG | Meeting Date | 12/02/2015 |  |
| Meeting Location | OCHA | Meeting Time | 3.30pm |  |
| Chair person | Typhaine Gendron | Meeting Duration | 1:30 hours |  |
| Minutes Prepared by | Remo Fambri, Associate IM officer UNHCR |  |  |  |
| Purpose of Meeting | - Update on assessments planned - Revision and endorsement of TORs - Next steps and workplan 2015 - Rapid needs assessments – field - AOB |  |  |  |
| Present at the meeting | OCHA – Typhaine UNHCR- Remo UNICEF – Hrayr UNRWA – August REACH – Josh Cash Consortium – Zineb UNDP - Bastien |  |  |  |

Summary of discussions and action points

|  | Update on assessments planned |  |
| --- | --- | --- |
|  | UNDP – update on methodology for assessments on tensions – Rapid Tensions Assessment Tool The Social Stability Core Group drafted a list of 18 key questions for partners to incorporate in their assessments (for Key Informant Interview) for baseline and post monitoring. The questions are grouped in 7 groups which are scored according to the questions result. Scores will be based on a 0 to 5 score to measure and possibly to be reported in a separate Activity Info database at cadaster level by the partners undertaking the assessment. The Rapid Tensions Tool will presented to the Intersector meeting and comments are expected by the AWG by 23 February. Action Points: Bastien to share documentation with Typhaine for sharing with the AWG AWG members by 23 February to Bastien Revel - UNDP |  |
| 2. | Revision and endorsement of TORs |  |
|  | - Decision on co-chairing of NGOs in the AWG. Participation of an NGO is recommended as co-chair of the AWG. Action Points: It is recommended that LHIF will appoint or recommend an NGO to represent the NGO forum Recommend participation of Government Representative Recommend field representation in AWG |  |
| 3. | Next steps and workplan until 30 June 2015 |
|  | - Scout on assessment capacity within partners to support the AWG and train them - Road show to identify partners in the field and raise awareness - Plan capacity building mechanism (training) for parnters to develop contextualized MIRA training with final outcome of Rapid Assessment Deployment, structures, system in place, coordination mechanism – a country level and field - Agree on platform where rapid assessment data will be hosted (possibly KOBO) - Set up an Activity Info DB for planned assessments - Create library on InfoHub for Assessments Action Points: Write work plan |
| 3. | Planned assessments |
|  | UNICEF= yes UNRWA= AUB survey 2015 to PRL countrywide as it will be compatible with the 2010 AUB survey. Currently the plan is being finalized. PRS will be included too. Survey to go out in the field in April. Results by June 2015 tentative. WB= planned assessment on community vulnerability ILO= assessment on poverty, employment rate |
|  | Next meeting = Thursday 12 March – 3:30 pm in OCHA |

Visit our Information Sharing Web Portal!

Click here to sign up to the Interagency Contact List for Lebanon!!