Meeting Minutes

Disability Taskforce

Tuesday 29 March, 2016

UNHCR Khalda, Amman

- Mapping Services

It was decided at the last meeting that more specifications on services provided should be added to the mapping services. The electronic version of the mapping services was shared to members. Organizations were asked to send updates and specifications for the final version.

- Final Review of ToR

The need for an information sharing platform on disability data was added as an objective of the ToR.

- Review of Draft DTF work plan

- The DTF work plan will be finalized in June 2016.

- Organizations gave positive feedback about using the guidelines during project management and the drafting of their own criteria for disability projects.

- A problem regarding the lack of care for birth- defects prevalent in new-born refugees was identified and will be addressed further in the future.

- There will be a quarterly review of the mapping services.

- Regarding the consolidation of the guidelines for finalization in June, it was suggested to send a survey collecting feedback about the guidelines from stakeholders. A workshop will then be held based on topics that were identified in the survey. The workshop will be held May 31st, June 1st, and June 2nd in Amman, Zaatari, and the camps.

- A leaflet based on the mapping of services exercise will be developed with information about what services for PWD are provided. Swiss Leg will undertake the development of this leaflet by May 30th. There should be a leaflet for each type of service for PWD (physical rehabilitation, assistance to people with hearing impairments, pyscho-social support etc.)

- It was suggested that during the quarterly review the Task Force will ensure that non-member organizations that offer services for refugees with disabilities are included in the information that will be presented on the leaflet.

- Next Steps for improving identification and consolidation of information on PwD

- A technical meeting will be held in order to come up with guidelines for the identification of the needs of persons with disabilities. A follow-up meeting will then be held on how the guidelines will be translated into needs assessment.  Data collection methods regarding identification of needs of PWD should be shared among members.

- Better outreach methods for PWD who face obstacles in reaching services due to discrimination and stigmas will be outlined by August/September 2016.

Action Points:

- Workshop for consolidating the DTF guidelines in Amman, Zaatari, and the camps will be held on May 30th, June 1st, and June 2nd. The survey regarding this workshop will be distributed 3 weeks before the meeting.

- Leaflet outlining the different services that are offered to persons with disabilities will be development by Swiss Leg by the end of May.

- Please send comments on the minimum qualifications required for staff delivering specialized services for PWD.

- Please send nominations for people with expertise on data management who should be invited to technical meeting on identification and qualifications of PWD.

- Please send what types of data collection tools are being used regarding identification of the needs of persons with disabilities by March 30th.

- Please send updated versions of mapping exercises by the March 30th.