| TITLE OF THE COORDINATION MEETING : Arsal Health coordination Meeting |  |  |  |
| --- | --- | --- | --- |
| Date | 14 March 2017 | Time | 13:00-14:30 |
| Location | UNHCR Zahle premises | Duration | 1h and half |
| Chair | Mona Kiwan-UNHCR |  |  |
| Attendance |  |  |  |

| Name | Organization | Email address | Phone Number |
| --- | --- | --- | --- |
| Mohammad Fliti | Arsal municipality council | mohamad.fliti@outlook.com | 70920790 |
| Naji Fliti | MOSA | najifliti@gmail.com | 70886734 |
| Sabine Abdul Sater | UNICEF | sabdulsater@unicef.org | 76 774417 |
| Dr Bassem Al Qalleeh | URDA/ EL Rahma Field Hospital Arsal | aarsal.mc@urda.org.lb | 76426878 |
| Khaled Osman | MSF-ch | msfch-bekaa-socialteam@geneva.msf.org | 71648475 |
| Dr Yasser El Hajji | El Amal Medical Centre | Star98319@gmail.com | 71 930825 |
| Omar Ajami | IMC | oajamy@InternationalMedicalCorps.org | 76 838004 |
| Samah Hatoum | IMC | shatoum@InternationalMedicalCorps.org | 70 674587 |
| Hady Hoblous | TDH | cm.specialist@tdhitaly.org | 81 789814 |
| Tarek Mazloum | Beyond | tarek_mazloum@hotmail.com | 70 129947 |
| Mahmoud Houjeiry | Beyond | beyondarsal@gmail.com | 03 237292 |
| Rajaa Halabi | UNHCR | Halabi@unhcr.org | 76421565 |
| Mona Kiwan | UNHCR | kiwanm@unhcr.org | 79160198 |

| 1.0 | Follow on the action plan from the previous coordination meeting | ACTION | DUE DATE |
| --- | --- | --- | --- |
| 1.1 | Reporting of communicable diseases training: -PHC, health centres, field hospitals, ROV Training on the reporting of communicable diseases by MoHP-ESU; To include in the training detection and referral of cases having/suspected having tuberculosis by IOM and Health access by UNHCR -For OV we will include ORS and diarrhea management; -Share the list of OV with UNHCR and to include Lebanese and Syrian refugees (to state which one are able to go outside Arsal) by 24th of March 2017 | -Wednesday 22nd March: PHC and health centers /Attendees names to be shared by Monday the 20th of March -Wednesday 29th March: Field hospitals/ /Attendees names to be shared by Monday the 27th of March -Wednesday 05 April: OV training / Attendees names to be shared by the third of April -Share list of Arsal OV | 22 March 2017 from 09:00 am till 13:30 29 March 2017 from 09:00 am till 13:30 05 April 2017 from 09:00 am till 13:30 24th of March 2017 |
| 1.2 | Hepatitis B vaccine -To check with IMA if they provide Hep B vaccination for newborn in their facility -MSF-ch will check if they can receive newborn from AMC and IMA facilities for Hep B vaccination | Same action to be followed | 20 March 2017 |
| 1.3 | Mapping of actual ongoing health/mental health activities: -4 W Matrix to be developed: UNHCR will circulate the matrix to be filled by NGOs -Developing a specific health services Leaflet for Arsal | Last inputs to be received by Thursday the 16th of March | 16th of March 2017 |
| 1.4 | Decision for the coordination meeting co-chair -Dr Bassem El Qalleeh from URDA and Dr Beshr El Khatib from QRCS volunteered to co-chair the group -Attendees agreed to do the voting through Survey Monkey -Co-chair to be changed each 6 months in order to give the opportunity for everybody to co-chair -UNHCR, UNICEF and MOSA will be neutral and won’t participate in the voting -The NGOs and health centres who will be invited to participate in the Monkey survey are: Municipality, MoPH, Amel, IMC, QRCS, URDA, MCA field hospital, AMC field hospital, IMA, Beyond, El Amal health centre, New Arsal health centre , MSF-ch, ICRC | -UNHCR will send a mail when launching the Survey Monkey; -If any entity, NGO who was not present in the meeting and wishes to be neutral and to not participate in the voting to inform UNHCR by Monday the 20th of March 2017 | Within March 2017 |
| 2.0 | Discussion on the pressing health/Public health/ mental health needs and other challenges | ACTION | DUE DATE |
| 2.1 | Due to the desludging issue, Beyond distributed in coordination with MoPH, over 15 days, Aquatab and ORS that supposed to reach all houses and informal settlements in Arsal. Attendees reported an increase in the incidence of waterborne diseases and hygiene related diseases (lice, scabies) due to the situation, therefore UNHCR recommended to receive concrete information about the events or cluster of cases in order to provide a comprehensive response: to send by mail concretely the following information: -Informal settlements or collective shelters location / P code/number of refugees residing in the IS -Chawish contact details and other focal person (could be family member of one of the cases affected) -Event description: number of cases of the event in question, time of onset of symptoms -If Any NGO did WASH or health activities -Please share the mail with UNICEF WASH coordinator: RefBekaaEW@unicef.org And with UNHCR health coordinator: lebzaphu@unhcr.org And with MoPH-ESU in case of communicable diseases: esubekaa@gmail.com | Partners to kindly follow the reporting mechanism | Regularly |
| 2.2 | Rumours about infestation of lice and scabies in school | To contact education sector in order to understand the situation | 17 March 2017 |
| 3.0 | Partners update | ACTION | DUE DATE |
| 3.1 | El Amal health centre is coordinating with MopH in order to receive vaccination |  |  |
| 3.2 | -IMC finalized recruitment and training of five mental health OV on the detection and referral of cases having MH disorders; They will continue the training on topics like CP, SGBV core concept and referral -IMC reported that within Amel PHC, the GP trained on MH gap is seeing between 20 to 30 patients per month | To refer the cases in need for MHPSS to Amel PHC where the Psychotropic and neuroleptic medication is available | Regularly |
| 4.0 | Upcoming trainings/opportunities for training | ACTION | DUE DATE |
| 4.1 | 19 OVs (under IRC support) will be trained for diarrhea management and ORS use (by UNICEF) as well for reporting of cases having or suspected having tuberculosis (by IOM) and health access (by UNHCR) |  | 15 March 2017 |
| 5.0 | AOB | ACTION | DUE DATE |
| 5.1 | ORS distribution to PHCs | Partners to report to UNHCR by mail whether their supported health centers received ORS | 16 March 2017 |