| TITLE OF THE COORDINATION MEETING : Arsal Health coordination Meeting |  |  |  |
| --- | --- | --- | --- |
| Date | 14 March 2017 | Time | 14:00-15:30 |
| Location | UNHCR Zahle premises | Duration | 1h and half |
| Chair | Rajaa Halabi-UNHCR |  |  |
| Attendance |  |  |  |

| Name | Organization | Email address | Phone Number |
| --- | --- | --- | --- |
| Hassan Kajieh | QRC | Hassan-kajieh@hotmail.com | 70884373 |
| Merii Fliti | Amel | meriiflity@hotmail.com | 71813880 |
| Kreyda Sadeek | El Amal Medical Centre | Alamal.a.m.c@gmail.com | 03/147891 |
| Dr Bassem Al Qalleeh | URDA/ EL Rahma Field Hospital Arsal | aarsal.mc@urda.org.lb | 76426878 |
| Khaled Osman | Msf-ch | msfch-bekaa-socialteam@geneva.msf.org | 71648475 |
| Dr. Bilal Kassem | Msf-ch | Msfch-bekaa-man@geneva.msf.org | 71801359 |
| Soma Al Ahmar | Msf-ch | Msfch-bekaa-socialteam@geneva.msf.org | 71706469 |
| Dr Yasser El Hajji | El Amal Medical Centre | Star98319@gmail.com | 71 930825 |
| Beshr Al Khateeb | QRC | beshralkhateeb@gmail.com | 81738891 |
| Samah Hatoum | IMC | shatoum@InternationalMedicalCorps.org | 70 674587 |
| Nour Fliti | TDH | n.fliti@tdhitaly.org | 81 789814 |
| Maya Dalloul | NRC | Maya.dalloul@nrc.no | 70999082 |
| Nadeen Noor Al Hebsh | UNICEF | nalhbsh@unicef.org | 70996604 |
| Rajaa Halabi | UNHCR | Halabi@unhcr.org | 76421565 |

| 1.0 | Follow on the action plan from the previous coordination meeting | ACTION | DUE DATE |
| --- | --- | --- | --- |
| 1.1 | Reporting of communicable diseases training: -PHC, health centres, field hospitals health staff and IRC/UNHCR ROV’s where Trained on the reporting of communicable diseases by MoHP-ESU and on the training on the detection and referral of cases having/suspected having tuberculosis by IOM and Health access by UNHCR -For ROV’s the training included ORS and diarrhea management; | -Wednesday 22nd March: PHC and health centers -Wednesday 29th March: Field hospitals | done done |
| 1.2 | Hepatitis B vaccine -To check with IMA if they provide Hep B vaccination for newborn in their facility. | Referral of new born to Irshad, Amel health centres |  |
| 1.3 | Mapping of actual ongoing health/mental health activities: -4 W Matrix developed and circulated -Developing a specific health services Leaflet for Arsal | Leaflet to be kindly prepared by Dr. Bassem | End of April 2017 |
| 1.4 | Decision for the coordination meeting co-chair -Dr Bassem El Qalleeh from URDA to Co-chair the working group based on the results of the voting through Survey Monkey |  |  |
| 2.0 | Vaccination |  |  |
| 2.1 | New-born in the field hospitals for Hep B - MSF: do provide Hep B only for deliveries that take place in their clinic. - Irchad PHC do not have full capacity to absorb all the new-born babies for hep B vaccination also to note that they do close in the afternoon and on the weekend. - AMC do not have Hep-B vaccination and they inform the families to approach al Irshad clinic; - No specific referral pathway to Irshad; - No referral pathway for Hep B vaccination; - Around 200 deliveries per month in Arsal. | - MSF to check if they can receive the new born kids for vaccination after working hours. - The working group recommended that Al amal to receive Hep B vaccination- discussion to be held with MoPH through UNHCR/UNICEF - Follow with MOPH if they can supply the field Hospitals and delivery centers with Hep B through Amel PHC (Follow up with MoPH and Amel). - To collect the data of number of deliveries happening in the health facilities and the number of Hep B vaccination done for the new-born for the past 3 months Jan to Mar 2017 (Data to be share with Dr Bassem, compiled and later shared with the Arsal working group for discussion) | 30-4-2017 End of April 2017 End of April 2017 End of April 2017 |
| 2.2 | IN Outskirts of Arsal |  |  |
|  | - Around 300 kids where vaccinated in UNICEF last campaign during the winter distribution campaign - Amel PHC are receiving patients coming from the outskirts and they are providing vaccination for the kids - MSF: Vitamin A supplement being distributed in the outskirts for pregnant women; in line with the increased new born malformation as reported by the working group (no concrete data) there were suspicion of correlation with vita A provision outside the MoPH policies and procedures. | - UNICEF To follow with MOPH if Beyond can do the vaccination campaign on regular bases - To monitor the number of kids coming from the outskirts of Arsal and if they are receiving from 17 to 30 April. - Dr. Bassem to follow on vit A provision (by whom, quantity prescribed, available medical order…) | May 2017 2-5-2017 End of April 2017 |
| 2.3 | For Medical Staff |  |  |
|  | - No control on the vaccination of the staff especially within the organization supporting PHC’s and Field Hospitals - All MSF staff are vaccinated | - Amel to check if they can support with the vaccination process of all health staff. - UNICEF/UNHCR to follow up with MOPH and if they can support with the vaccination | End of April 207 |
| 3 | - OV Trainings plan and evaluation of the trainings done to health centres and Field Hospitals |  |  |
|  | - Arsal dispensaries started reporting of communicable diseases to MoHP-ESU - Not all dispensaries reported to MOPH after the training - None of the ROV’s approached the PHC’s to receive ORS - Al Amal PHC is in need for ORS since the amount they received is not enough - TdH have 12 OV’s, NRC have 12 and IMC have 5 ov’S - To do an TOT training for OV’s - PHC’s to supply the ROV’s with the ORS. If we can do the training on a Friday | - UNHCR to follow with MOPH-ESU on which dispensaries did not report to follow with them in order to solve the reasons behind not reporting. - To request from UNICEF ORS based on the need, by sharing the needs with dr. bassem that will compile a list and follow with UNICEF. - To set a date and Time. | 15-4-2017 |
| 2.0 | - Discussion on the pressing health/Public health/ mental health needs and other challenges | - ACTION | DUE DATE |
| 2.1 | - to follow with MoPH-esu in order to know which phc’s started reporting after they received the training in order to follow with dispensaries not reporting yet | Follow with Zeina | End of April |
| 4.0 | Wash Situation | ACTION | DUE DATE |
| 4.1 | - desludging activities started - desludging is taking place in dalayel el barak which is near the town (2 KM). - Hygiene promotion sessions are taking place - MSF reported that there exist Diarrhea cases in Ras al Sarj Area as reported by patients living in that area. | IMC and TdH to send OV to do a rapid assessment | 15-4-2017 Done: IMC ROV’s team visited the area and they didn’t identify any cases. TdH ROV’s identified individual |
| 5.0 | AOB | ACTION | DUE DATE |
| 5.1 | Needs and challenges: |  |  |
|  | Mental Health: - IMC they do have around 20 to 30 patients per month - Al amal are receiving around 45 cases per week and they have around 150 active cases. - No capacity to fully cover the gap in the medication | Al amal to refer patients that they can’t support them with Medication to IMC/Amel |  |
|  | - Gap in the chronic and acute medication |  |  |