| TITLE OF THE COORDINATION MEETING : Arsal Health coordination Meeting |  |  |  |
| --- | --- | --- | --- |
| Date | 09 May 2017 | Time | 13:00-14:30 |
| Location | UNHCR Zahle premises | Duration | 1h and half |
| Chair | Mona Kiwan-UNHCR |  |  |
| Attendance |  |  |  |

| Name | Organization | Email address | Phone Number |
| --- | --- | --- | --- |
| Mohammad Jebawi | Arsal Municipality |  | 03165949 |
| Hassan Zaarour | Arsal Municipality |  | 76663691 |
| Nazih | Arsal Municipality |  | 03088430 |
| Hassan Kajieh | QRC | Hassan-kajieh@hotmail.com | 70884373 |
| Merii Fliti | Amel | meriiflity@hotmail.com | 71813880 |
| Dr Bassem Al Qalleeh | URDA/ EL Rahma Field Hospital Arsal | aarsal.mc@urda.org.lb | 76426878 |
| Khaled Osman | Msf-ch | msfch-bekaa-socialteam@geneva.msf.org | 71648475 |
| Soma Al Ahmar | Msf-ch | Msfch-bekaa-socialteam@geneva.msf.org | 71706469 |
| Dr Yasser El Hajji | El Amal Medical Centre | Star98319@gmail.com | 71 930825 |
| Hiba Chamoun | Intersos | legal.bekaa.lebanon@intersos.org | 71673036 |
| Ihab El Haddad | Intersos | Legal.assistant1987@gmail.com | 03172114 |
| Maya Dalloul | NRC | Maya.dalloul@nrc.no | 70999082 |
| Rajaa Halabi | UNHCR | Halabi@unhcr.org | 76421565 |
| Mona Kiwan | UNHCR | Kiwanm@unhcr.org | 79160198 |

| 1.0 | Follow on the action plan from the previous coordination meeting | ACTION | DUE DATE |
| --- | --- | --- | --- |
| 1.1 | OV Training: on the Reporting of communicable diseases training by MoPH-ESU, the training on the detection and referral of cases having/suspected having tuberculosis by IOM, Health access by UNHCR, diarrhea management and ORS utilization by UNCIEF | Training to be held by UNHCR,UNICEF, MoPH-ESU and IOM | 19th of May 2017 |
| 1.2 | Mapping of actual ongoing health/mental health activities: | Soma from MSF-ch will support in developing the health info brochures to include access to vaccination specially Hep B vaccination for new born Posters for vaccination/health awareness brochures on vaccination to be posted in the health facilities Community Awareness/ Education on vaccination | End of May 2017 End of May 2017 Regularly |
| 1.3 | Vaccination |  |  |
| 1.3.1 | Hepatitis B vaccine of new born -A preliminary observation of the number of deliveries and number of vaccination of new-born for Hepatitis B during the period 01-04-2017 till 22-04-2017 showed that only 15% of the newborn were vaccinated in the first 24 hours of birth for Hep B. -MoPH is ready to increase the Hep B vaccines in case the utilization rates increased; -Al Amal received the vaccination and open weekends and Irshad open Fridays | Referral pathway to be established in order that all newborn to receive the Hep B vaccination in the first 24 hours of birth | End of May 2017 |
| 1.3.2 | Vaccination in the outskirts of Arsal: Advocacy continues in order that the outskirt of Arsal to be covered as soon as possible by regular EPI activities; |  |  |
| 1.3.3 | For Medical Staff : -MoPH approved that the field hospital staff to receive the measles vaccination form Amel PHC; therefore Amel will receive the names of field hosp staff in need for measles vaccination and will share it with MoPH and will administer the vaccination; -Field hosp staff advocated for the need for Hepatitis B vaccination as well; | Field hosps staff to prepare a letter in order to be sent to MoPH that includes the need for vaccination coverage for Hep B and measles | End of May 2017 |
| 2.0 | Birth Registration Presentation by Hiba Chamoun (Intersos) | ACTION | DUE DATE |
| 2.1 | Presentation done by Hiba from Intersos | Brochures can be requested by sending mail to Hiba Chamoun: legal.bekaa.lebanon@intersos.org | Regularly |
| 3.0 | Training Plans/ Feedback and recommendations following previous trainings held |  |  |
| 3.1 | -MopH- ESU training on the reporting of communicable diseases for OV: reporting mechanism: It was agreed that the OVs to report to their supervisors the suspected cases detected and will refer them to the PHC; the supervisors will inform UNHCR about the suspected cases and UNHCR informs MoPH; In the same time after confirmation, the PHC will report the case to MoPH-ESU; -Cluster of cases to be reported directly to UNHCR an IA WASH -Discussion about having a group Whatsap for the follow up of the OVs trained and more follow up meetings to be held with them |  |  |
| 3.2 | ORS utilization by health centres and OV: UNICEF and MoPH want to refill the stock of ORS in the health centres | -Only Al Amal health centre is in need for 300 sachets/month- the other facilities still have stocks -OVs to request the ORS from the health centres | May 2017 |
| 3.3 | Health centres reporting to MoPH-ESU: Still some health centres are not reporting accordingly following the training done | -Reporting of the field hospitals to be separated from the health centres -The AMC field hospital has to report accordingly -New Arsal and and El Aa2idoun Health centres need to start reporting | May 2017 |
| 4.0 | Discussion on the pressing health/Public health/ mental health needs and other challenges | ACTION | DUE DATE |
| 4.1 | Access of patient with MH disorders to psychotropic medications | Referring the cases in need for psychotropic medications to Amel PHC | Regularly |
| 5.0 | Partners update | ACTION | DUE DATE |
| 5.1 | AMC started closing at 4pm mainly due to financial constraints |  |  |
| 5.2 | New Arsal dropped in number of monthly consultations after QRCS stopped the financial support |  |  |
| 5.3 | QRCS will run soon a Mammography through MMU |  |  |
| 6.0 | Wash Situation | ACTION | DUE DATE |
| 6.1 | Al Amal, Amel health centers and MCA OVs can be contacted for an outreach health assessment and response |  |  |
| 7.0 | AOB | ACTION | DUE DATE |
| 7.1 | Issues in the outreach vaccination | Dr Bassem will inform MoPH (Miss Safaa Sleiman) about the concern | May 2017 |
| 7.2 | Al Isaaf El Chaabi PHC to be contacted in order to start coordinating with the group |  | May 2017 |