| TITLE OF THE COORDINATION MEETING : Arsal Health coordination Meeting |  |  |  |
| --- | --- | --- | --- |
| Date | 08 August 2017 | Time | 13:00-14:30 |
| Location | UNHCR Zahle premises | Duration | 1h and half |
| Chair | Mona Kiwan-UNHCR |  |  |
| Attendance |  |  |  |

| Name | Organization | Email address | Phone Number |
| --- | --- | --- | --- |
| Joseph Daoud | LRC | Localdmuzahle@hotmail.com | 03 271099 |
| Merii Fliti | Amel | meriiflity@hotmail.com | 71813880 |
| Dr Bassem Al Qalleeh | URDA/ MCA | basemalqalleeh@yahoo.com | 76426878 |
| Kamel Kalaany | ACF | kkalaany@lb.acfspain.org | 03 580170 |
| Alma Migens | ACF | amigens@lb.acfspain.org | 81686856 |
| Jana Sarout | IOCC | Jsarout@iocc.org | 70196340 |
| Elie Saade | HI | dvfppo.ZH@hi-emergency.org | 03641589 |
| Dr Yasser El Hajji | El Amal Medical Centre | Star98319@gmail.com | 71 930825 |
| Roba Zaem | IRC | Roba.Zaem@rescue.org | 76 757559 |
| Rana Hmaymess | IRC | Rana.Hmaymess@rescue.org | 76 666 263 |
| Akram Kaakour | Mercycorps | akaakour@Mercycorps.org | 03586313 |
| Rajaa Halabi | UNHCR | Halabi@unhcr.org | 76421565 |
| Mona Kiwan | UNHCR | Kiwanm@unhcr.org | 79160198 |

| 1.0 | Follow on the action plan | ACTION | DUE DATE |
| --- | --- | --- | --- |
| 1.1 | Field hospitals management to prepare a letter in order to be sent to MoPH that includes the need for vaccination coverage for Hep B and measles: This action is still pending waiting to know which staff from both AMC and MCA field hospitals will remain in Arsal, knowing that some staff left to Idlib: *From AMC: 10 doctors and health staff left in addition to the management. Knowing that dialysis is still running. *From MCA: 2 staff+ 1 surgeon left To note that so far there is no general surgeon in Arsal left and there were recommendation from attendees that advocacy is needed near authorities in order to prevent delay of the referral of critical cases to hospitals outside Arsal through LRC. LRC reported that meetings are being held between LRC representative and the authorities in order to follow on this issue. | Follow up with AMC field hospital in order to understand who took over the management and if any existing function gap | Aug 2017 |
| 1.2 | Increase the access of newborn babies to Hepatitis B vaccination by developing referral pathways : MSF-ch will start vaccination in August 2017: MSF-ch were not present in the meeting therefore UNHCR will follow with them in order to understand whether the activity was implemented |  | Aug 2017 |
| 1.3 | OV/CHW/Front line staff Training in order to strengthen the community surveillance and health access and Prevention of dehydration correlated to the Dislodging issue in Arsal: It was agreed that 70 WASH frontline staff and community members under Mercycorps and ACF need to be trained on the reporting of communicable diseases and ORS use. These front line staff cannot cross to outside Arsal. IRC is as well interested to train its staff. The challenge is the access of MoPH and UN agencies to Arsal to implement the training. Dr Bassem Qalleeh volunteered to receive the curriculum and does the training. A coordination between MoPH, UNICEF, and UNHCR is needed in order to have a decision on this matter. |  |  |
| 1.4 | Enhancing the Epidemiological surveillance and the reporting of the communicable diseases to MoPH-ESU: - MoPH-ESU requested to collect stool specimens on a weekly basis from cases having diarrhea and admitted to MCA (as first stage), from different age groups: activity not started because of the situation but it will be resumed as soon as possible in coordination between Dr Qalleeh and Mrs Rania Sarkis -New Arsal and El Aa2idoun Health centers need to start reporting: Dr Bassem volunteered to follow with El Aa2idoun and Elie Saadeh from HI for New Arsal |  |  |
| 1.5 | Reporting to the MoPH the Maternal, neonatal mortality and the Monthly reporting forms: So far, no health center/field hospital reported and it was recommended to start sharing the reports with UNHCR as soon as possible so UNHCR to share them with MoPH |  |  |
| 2.0 | Post emergency response evaluation | ACTION | DUE DATE |
| 2.1 | Issues discussed about the health staff who left Arsal and the need for quick referral through LRC (discussed in the first part of the minutes) |  |  |
| 2.2 | Authorities are actually allowing the transfer of resources to Arsal health centers and health facilities smoothly |  |  |
| 2.3 | LRC briefed about their response in Arsal recent clashes. Moreover, LRC inaugurated a center in Qaa for the response in case of issues arising in Ras Baalbeck and MAQ. | Arsal response report will be shared with the minutes |  |
| 3.0 | WASH Updates |  |  |
| 3.1 | -Lost- ACF-Mercycorps are the WASH partners in Arsal doing mainly water tracking/desludging -ACF stopped 20 days in Arsal due to many reasons but actually they are now back to full capacity through suppliers; ACF: Will be coordinating with the mayor for the dumping site in Arsal -In some sites, ACF and Mercycorps WASH committees aren’t reporting accordingly the existing concerns and issues. | For any referrals, please send an email to RefBekaaEW@unicef.org and to Lebanon Zahle Health Referrals LEBZAPHU@unhcr.org | Regularly |
| 4.0 | Partners Update | ACTION | DUE DATE |
| 4.1 | HI: will stop activities in AMC / will continue in New Arsal |  |  |
| 4.2 | El Amal: reported that one doctor and one nurse from their staff left to Idlib |  |  |
| 4.3 | Amel: recruited a midwife for their health centre |  |  |
| 5.0 | AOB | ACTION | DUE DATE |
| 5.1 | IRC start receiving CP/SGBV referrals from North Bekaa |  |  |