| TITLE OF THE COORDINATION MEETING : Arsal Health coordination Meeting |  |  |  |
| --- | --- | --- | --- |
| Date | 14 November 2017 | Time | 11:00-12:30 |
| Location | UNHCR Zahle premises | Duration | 1h 30min |
| Chair | Mona Kiwan-UNHCR | Co-chair | Dr Bassem Al Qalleeh (URDA-MCA) |
| Attendance |  |  |  |

| Name | Organization | Email address | Phone Number |
| --- | --- | --- | --- |
| Rania Sarkis | MoPH-ESU | rania-sarkis@outlook.com | 70706259 |
| Fatima Rachini | LRC | fatima.Rachini@redcross.org.lb | 03805746 |
| Merii Fliti | Amel | meriiflity@hotmail.com | 71813880 |
| Dr Bassem Al Qalleeh | URDA-MCA | basemalqalleeh@yahoo.com | 76426878 |
| Kamel Kalaany | ACF | kkalaany@lb.acfspain.org | 03580170 |
| Lamis Flaha | ACF | Lflaha@lb.acfspain.org | 03503568 |
| Samah Hatoum | IMC | shatoum@internationalmedicalcorps.org | 70674587 |
| Becky Oba | MSF | msfch-bekaa-pmr@geneva.msf.org | 76512742 |
| Marwa Bakabas | Sawa for development and Aid | Marwa.b@sdaid.org | 81651937 |
| Feras El Ghadban | Sawa for development and Aid | FerascH33@gmail.com | 76864721 |
| Jana Siu | Sawa for development and Aid | janysiu@gmail.com | +19257888812 |
| Mona Kiwan | UNHCR | Kiwanm@unhcr.org | 79160198 |

| 1.0 | Follow on the 2017 action plan | ACTION | DUE DATE |
| --- | --- | --- | --- |
| 1.1 | Measles and hepatitis B vaccines not available to be provided to healthcare staff | Follow up with Miss Safaa Sleiman | Nov 2017 |
| 1.2 | MSF-ch receiving hepatitis B for new born and reporting to MoPH | Dr Bassem calculate roughly the number of deliveries and those who received vaccination | End of Nov 2017 |
| 1.3 | Accelerated Immunization Activity (AIA): -Amel is the NGO partner supporting at door to door level; -Referral for completion of vaccination and for acute malnutrition management will be done to Amel health center. -Activity started at HH level November 13th. -Mercycorps/ ACF, LOST: will support Amel teams in informal settlements levels; noting that Amel will provide direct vaccination activities in the IS. - Mercycorps/ ACF, LOST will receive the training by November 15th. -1 staff (nutritionist) from Mercycorps will be trained for acute malnutrition management and will receive referrals in Amel Health center. | Advocacy to integrate acute malnutrition management activities inside a health centre in Arsal | Early 2018 |
| 1.4 | Dialysis: Istijaba NGO (Kuweit NGO) is the actual donor for dialysis in AMC field hospitals. Rumors about issues in funding and field hospital may start taking fees from the patients for dialysis sessions. |  |  |
| 1.5 | Delay of referral of patients in need for hospitalization outside Arsal still occurring (between 3 to 5 hours waiting time)- e.g., for Myocardial Infarction it takes around 2.5 hours | Advocacy needed between LRC and authorities | Ongoing |
| 1.6 | Only 3 out of more than 10 patients referred to labwe PHC by MSF-ch actually went- this raise the need to urgently having YMCA contracting at least two health centers in Arsal | Advocacy with MoPH for YMCA in Arsal | Ongoing |
| 2.0 | Arsal Action Plan – midyear 2018 | ACTION | DUE DATE |
| 2.1 | The Action plan was reviewed and the required below fund was added to the Outcome 3: Access to Mental Health and Psycho-social support services improved: -Community mental health through five OVs serving all IS residents (around 40,000 ind.) Fund needed: $9,000 - Psychotropic Medication for Amel health center (180 beneficiaries /6 months) Fund needed: $15,000 -2 Trainings on mental health detection and referral for 30 participants Fund needed: $3600 |  |  |
| 3.0 | Partners update | ACTION | DUE DATE |
| 3.1 | -IMC MHPSS will have a detection and referral training in Northern Bekaa (27-28 Nov); invitation will be circulated -After new year CHW IMC will stop because of lack of fund | IMC to consider keeping the Arsal CHW | 2018 |
| 3.2 | Amel outreach team screening for NCD above 40 and referring to the health center for follow up and treatment |  |  |