## 2015 Sector WP (hidden)
Jordan Food Security Sector Working Group (FSSWG) Workplan 2015
Key Areas of Work |  | Activity | Sub-Activities | Q1 | Q2 | Q3 | Q4 | Remarks
A. FSSWG Workplan | Strengthen coordination | Revisit the co-leadership role | Revise and agree on division of tasks between co-chairs | x
|  | Revise FSSWG TOR | Review, update and implement the TOR | x
|  |  | Review, update and implement section on co-chair's responsibilities | x
|  | Strenghten sub-national coordination | Identification of FSSWG focal points to participate in the urban/rural coordination meetings/structure on a rotational basis | x
|  | Strengthen FSSWG internal coordination with group members | Conduct a half-day workshop to identify ways to improve participation and regular contributions to the sector | x
|  |  | Co-chairs to engage in bilateral communication with members to discuss participation | x
|  | Strengthen FSSWG Linkages coordination withLivelihood task force | Activate livlihood task force ,review,update and implement the TOR and action plan. Updating Livlihood task force contacts and liase closley with MoL,ensure iformation sharing between the two bodies
Continuing humanitarian enclose coordination
Strengthen rferral system (other system referred to WFP and internal referral system).Approval process and react towards referral system
| Capacity development | Organize capacity development trainings to members of the FSSWG | Organize 2-3 trainings based on the needs of the FSSWG members | x | x | x | x
|  | Support GoJ in the rolling out of the trainings for Jordan on food security (MoA, MoL, MoH, DoS) | Support trainings for GoJ staff and FSSWG members | x | x | x | x | Ongoing - follow up
|  | Capacity assessment training | Organize 2-3 trainings based on the needs of the FSSWG members.Translation: online training needed to be translated to Arabic
| Planning and Strategy Development | Continue the strategic planning for the Food Security Sector in Emergencies/Refugee component within the Jordan Response Plan (JRP) and the Regional Refugee and Resilience Response Plan (3RP) frameworks | Strategic planning and coordination of activities in line with the refugee needs, as part of the mid-term review and the end of year preparations for 2016 planning |  | x |  | x
|  | Address the immediate and short-term needs of people in need | (Are we only referring to vulnerable Jordanians here? This will affect how we word the sub-activities) Ensure | x
|  | Establish links between the FSSWG coordination and the Livelihoods and Food Security Task Force | Reflect linkages to resilience in meetings and strategic planning Ensure information sharing between the two bodies. | x | x | x | x
|  | Review contingency/emergency preparedness plan for the sector | Review and update contingency/emergency preparedness plan for the sector | x | x | x | x | In agreement with ISWG and IATF
| Advocacy and Resource Mobilization | Advocate with donors, other sectors and key stakeholders for the prioritisation of food in emergencies | Food in emergencies is included and prioritised by donors and other key stakeholders as part of the communication strategy and planning of FSSWG members | x | x | x | x
|  | Resource mobilisation at the sectoral level | Key messages on fundraising for food security to be communicated to donors, including cross-cutting issues | x | x | x | x
|  | Advisory role for the ERF proposal revision process and liaison with OCHA Humanitarian Financing Section and other sources of funding | Critical needs of food security sector are integrated as part of lifesaving intervention so as to access humanitarian rapid funding such as ERF and other funding opportunities. | x | x | x | x
|  | Regularly update food security financial tracking system in relation to requirements | Update the food security financial tracking system on a quarterly basis | x | x | x | x
|  | Advocacy and training | FSSWG Common advocacy message
Advocacy for other refugees populations
| Information Management, Monitoring & Reporting | FSSWG members to update their food-related activities under ActivityInfo on a monthly basis (prior to the 8th of each month) | Members to submit data prior to the 8th of each month | x | x | x | x
|  | Collect, analyse and disseminate food assistance data through the 4Ws in collaboration with food security sector partners | 4Ws are produced, regularly updated and disseminated with key stakeholders | x | x | x | x | IM - M&R
|  | Facilitate the capacity building of partners on data collection, analysis, response planning and monitoring | Sector Working Group partners are oriented on Information Management products | x | x | x | x | IM - M&R
|  | Conduct field based monitoring and evaluation and in depth analsyis on impact of food security interventions in Jordan, using results to contextualise ongoing FSSWG activities | Develop reports analysing programmes | x | x | x | x | IM - M&R
|  | Regular analysis of Food Security Sector needs and identified gaps | Conduct quarterly needs and gaps analysis as per information collected through ActivityInfo online database | x | x | x | x
|  | Produce and disseminate information and gap analysis (dashboards, maps, etc) to all stakeholders | Food Security updates and gap analysis are regularly produced and shared with Sector Working Group members and key stakeholders. | x | x | x | x | IM - M&R
|  | Beneficiary information sharing | verification of beneficiaries information
| Protection | Maintaining protection standards in food assistance to avoid possible violations of beneficiaries right to receiving equal and equitable assistance | Sharing of information on best practices in maintaining protection in delivering food assistance within the group | x | x | x | x | Linking with the Protection WG
|  | Sharing regular feedback/observations related to the impact of reductions in assistance on Syrian refugees in Jordan | Members of the group to share regular feedback on the impact of reductions in assistance on Syrian refugees in Jordan | x | x | x | x
|  | Protection in Food security training | 6 month position for protection officer to be based on WFP
Access and protection in food security
| Gender mainstreaming | Strengthen capacity of food security sector members on gender sensitive response | Conduct refresher sessions on Gender mainstreaming/Gender Marker and related tools to strenghten the quality and gender sensitivity of food security responses | x | x | x | x
|  | Strengthen capacity of FSSWG on Gender marker | organize 2-3 trainings based on the needs of the FSSWG members
B. Cross-Sector Collaboration | Basic Needs | Coordinate with the ISWG on the minimum expenditure baskets
|  | Liaise with group regarding planned implementation of voucher/OneCard system | Develop capacity of Basic Needs sector to implement planned voucher system and coordinate regarding the OneCard platform | x | x | x | x | In collaboration with the Basic Needs WG
| Protection | Continue coordination of FSSWG members participation at the InterAgency SGBV/CP SOPs trainings to strengthen the quality and capacity response of food security partners and the referral pathways | Partners are trained on CP and GBV SOPs and better oriented on how to respond to such issues -- Feedback from the FSSWG members as well | x | x | x | x | In collaboration with SGBV and CP sub-WG's
| PSEA | Ensure members incorporate measures for PSEA in their programmes | Conduct awarenes raising sessions on the available agency-specific complaints mechanisms and ways to refer cases of sexual exploitation and abuse and how to prevent their occurance | x | x | x | x
| SGFPN | Food Security Sector Gender Focal Points to provide regular updates on gender related issues, focusing on food security related matters | Activate and Liase with the Sector Gender Focal Points Network | x | x | x | x
| Nutrition & Education | Coordinate with the Nutrition sub-WG and Education WG | Participate in WG meetings in order to detect issues of relevance to the FSSWG and coordinate/share accordingly | x | x |  |  | In collaboration with the Nutrition sub-WG and Education WG
|  | Comprehensive multi-sector approach to nutrition | Coordinate with Nutrition working group in order to identify mutli-sector approch to nurtition progammes
| ISWG | Strenghten collaboration and communication with other sectors | Partners and beneficiaries are provided with relevant orientations and messages related to cross-cutting issues Closer links to other sectors on issues that impact food security interventions | x | x | x | x
|  | Contribution to need assessments JRP | update of JRP will be on mid of this year

## 2017 Sector Work plan (hidden)
Food Security Sector Workplan 2017
Key Areas of Work |  | Activities | Ownership | J | F | M | A | M | J | J | A | S | O | N | D | January Status | April Status | August Status | December Status | Comment/ Rationale
A. Food Security Sector Working Group Workplan | Sector Coordination | JRP/3RP process (2018-2020) Sector Programme Planning (Planning early) | All partners | [12 empty] | Not Started | bar: A; J to D
|  | Donor Coordination - future year ahead priorities (2017 - 2018) | Sector Chair | [12 empty] | Not Started | bar: F to A; A; D
|  | Review contingency/emergency preparedness plan for the sector | All partners | [12 empty] | Not Started | bar: M to A; J to A; N to D
|  | Resource mobilisation at the sectoral level and advocacy | Sector Chair/ All partners | [12 empty] | ongoing | bar: J to D
|  | Regularly update food security financial tracking system in relation to requirements | All partners | [12 empty] | ongoing | bar: M to A; J to A; N to D
| Internal procedure | Strategy /2017 FSSWG Workplan endorsement | All partners | [12 empty] | Not Started | bar: J to D
|  | Communications protocol and internal coordination between FSSWG members | All partners | [12 empty] | ongoing | bar: J to D
|  | Review of SOP and guidance documents | All partners | [12 empty] | Not Started | bar: J to D
|  | Mid-year review of structure and ToR | All partners | [12 empty] | Not Started | bar: J to D
|  | Mid-year survey of added value and suggestions | All partners | [12 empty] | Not Started | bar: J to D
| Reporting | ActivityInfo Reporting | All partners | [12 empty] | started | bar: J to D
|  | RAIS Reporting and beneficiaries cross-check | All partners | [12 empty] | not Started* |  |  |  | To Check if RAIS was used before by FSSWG | bar: F to D
|  | Utilizing services advisor to map the Food Security interventions | All partners | [12 empty] | Not Started | bar: M to D
|  | Quarterly review of reporting gaps across sector | Sector Chair/ Coordination unit | [12 empty] | Not Started | bar: A; A; D
|  | Facilitate the capacity building of partners on data collection, analysis, response planning and monitoring | Sector Chair/ Coordination unit | [12 empty] | ongoing | bar: J to D
|  | Conduct field based monitoring and evaluation and in depth analysis on impact of food security interventions in Jordan, using results to contextualise ongoing FSSWG activities | All partners | [12 empty] | Not started | bar: A; A; D
|  | Development of products for local/regional meetings | Sector Chair/ Coordination unit | [12 empty] | ongoing | bar: A; A; D
| Capacity development | Organize capacity development trainings to members of the FSSWG | Sector Chair/ All partners | [12 empty] | Not Started | bar: J to D
|  | Support GoJ in the rolling out of the trainings for Jordan on food security (MoA, MoL, MoH, DoS) | Sector Chair/ All partners | [12 empty] | Not Started | bar: J to D
|  | Capacity assessment training based on the needs of the FSSWG members | Sector Chair/ All partners | [12 empty] | Not Started | bar: J to D
| Operational Support | Formulate standard approach regarding identification and assistance towards JOR beneficiaries | All partners | [12 empty] | Not Started | bar: M to D
|  | Review of Minimum standards (also informed by MEB formulation) | All partners | [12 empty] | Not Started | bar: A; J to S; D
|  | Formulation of processes related to calls for proposals (HIP, JHF, BPRM) | Sector Chair / Coordination unit | [12 empty] | Not Started | bar: M to A; A; D
B. Cross-Sector Collaboration | Gender and Diversity | Development of joint (multi-agency) gender impact assessment | SGFP/ GenCap advisor/ All Partners | [12 empty] | started | bar: J to D
|  | Strengthen capacity of FSSWG on Age and Gender marker | SGFP | [12 empty] | ongoing | bar: J to D
|  | Implementation of action plan based on SGFP network workplan | Sector Chair/ SGFP | [12 empty] | ongoing | bar: J to D
| Basic Needs | Coordinate with the Basic Needs WG on the minimum expenditure baskets | Sector Chair/ All partners | [12 empty] | Not Started | bar: A; J to A; D
|  | Liaise with Basic Need WG regarding planned implementation of voucher/One Card system | FSSWG & BNWG | [12 empty] | Not Started | bar: A to A; D
| Protection | Continue coordination of FSSWG members participation at the Interagency SGBV/CP SOPs trainings to strengthen the quality and capacity response of food security partners and the referral pathways | Sector Chair/ All partners | [12 empty] | ongoing | bar: J to D
|  | Ensure members incorporate measures for PSEA in their programmes | All partners | [12 empty] | ongoing | bar: J to D
Capacity building of FSSWG members on protection mainstreaming and integration in food assistance programming and implementation
|  | Stock-taking of complaints mechanisms and investigation procedures * | Sector Chair | [12 empty] | ongoing | bar: J to D
| Livelihoods | Livelihoods and level of assistance | All partners ( FSSWG + LHH) | [12 empty] | Not Started | bar: M to A; D
| Health and Nutrition | Coordinate with the Nutrition sub-WG to promote for Comprehensive multi-sector approach to nutrition | Sector Chair/ All partners | [12 empty] | ongoing | bar: J to D
| Education | Coordinate with the Education WG ( school feeding programs). | Sector chair /All partners | [12 empty] | ongoing | bar: J to D
| JRP/JORIS | Facilitate participation of relevant ministry 2017-18 | Coordination Associate / Sector chair | [12 empty] | Not Started | bar: J to D
|  | JORIS upgrade and facilitating approvals via line ministries | All partners | [12 empty] | ongoing | bar: J to D
|  | Provide regular updates on connection and integration into JRP | Coordination Associate / Sector chair | [12 empty] | Not Started | bar: J to D
| ISWG | Strengthen collaboration and communication with other sectors by promoting Intersector Linkages | ISWG / Sector chair | [12 empty] | ongoing | bar: J to D
|  | Consolidate sector work plans to identify linkages and to providing support to Urban coordination forums as required | ISWG / Sector chair | [12 empty] | ongoing | bar: J to D
Note on C26: CRAWFORD Emma: Is this referring to FSS Gender Analysis by SGFPN?
Note on C27: CRAWFORD Emma: As for protection, we could include capacity building for partners on gender mainstreaming and integration in food assistance programming and implementation (including gender and age marker). This could be conducted by SGFPN.

## 2018 Sector Work plan
Food Security Sector Workplan 2018
Key Areas of Work |  | Activities | Ownership | J | F | M | A | M | J | J | A | S | O | N | D | January Status | April Status | August Status | December Status | Comment/ Rationale
A. Food Security Sector Working Group Workplan | Sector Coordination | JRP/3RP process (2018-2020) Sector Programme Planning (Planning early) | All partners | [12 empty] | Not Started | bar: A; J to D
|  | Donor Coordination - future year ahead priorities (2018 - 2019) | Sector Chair | [12 empty] | Not Started | bar: F to A; A; D
|  | Review contingency/emergency preparedness plan for the sector | All partners | [12 empty] | Not Started | bar: M to A; J to A; N to D
|  | Resource mobilisation at the sectoral level and advocacy | Sector Chair/ All partners | [12 empty] | ongoing | bar: J to D
|  | Regularly update food security financial tracking system in relation to requirements | All partners | [12 empty] | ongoing | bar: M to A; J to A; N to D
| Internal procedure | Strategy /2018 FSSWG Workplan endorsement | All partners | [12 empty] | Not Started | bar: J to D
|  | Communications protocol and internal coordination between FSSWG members | All partners | [12 empty] | ongoing | bar: J to D
|  | Review of SOP and guidance documents | All partners | [12 empty] | Not Started | bar: J to D
|  | Mid-year review of structure and ToR | All partners | [12 empty] | Not Started | bar: J to D
|  | Mid-year survey of added value and suggestions | All partners | [12 empty] | Not Started | bar: J to D
| Reporting | ActivityInfo Reporting | All partners | [12 empty] | started | bar: J to D
|  | RAIS Reporting and beneficiaries cross-check | All partners | [12 empty] | not Started* |  |  |  | To Check if RAIS was used before by FSSWG | bar: F to D
|  | Utilizing services advisor to map the Food Security interventions | All partners | [12 empty] | Not Started | bar: M to D
|  | Quarterly review of reporting gaps across sector | Sector Chair/ Coordination unit | [12 empty] | Not Started | bar: A; A; D
|  | Facilitate the capacity building of partners on data collection, analysis, response planning and monitoring | Sector Chair/ Coordination unit | [12 empty] | ongoing | bar: J to D
|  | Conduct field based monitoring and evaluation and in depth analysis on impact of food security interventions in Jordan, using results to contextualise ongoing FSSWG activities | All partners | [12 empty] | Not started | bar: A; A; D
|  | Development of products for local/regional meetings | Sector Chair/ Coordination unit | [12 empty] | ongoing | bar: A; A; D
| Capacity development | Organize capacity development trainings to members of the FSSWG | Sector Chair/ All partners | [12 empty] | Not Started | bar: J to D
|  | Support GoJ in the rolling out of the trainings for Jordan on food security (MoA, MoL, MoH, DoS) | Sector Chair/ All partners | [12 empty] | Not Started | bar: J to D
|  | Capacity assessment training based on the needs of the FSSWG members | Sector Chair/ All partners | [12 empty] | Not Started | bar: J to D
| Operational Support | Formulate standard approach regarding identification and assistance towards JOR beneficiaries | All partners | [12 empty] | Not Started | bar: M to D
|  | Review of Minimum standards (also informed by MEB formulation) | All partners | [12 empty] | Not Started | bar: A; J to S; D
|  | Formulation of processes related to calls for proposals (HIP, JHF, BPRM) | Sector Chair / Coordination unit | [12 empty] | Not Started | bar: M to A; A; D
B. Cross-Sector Collaboration | Gender and Diversity | Development of joint (multi-agency) gender impact assessment | SGFP/ GenCap advisor/ All Partners | [12 empty] | started | bar: J to D
|  | Strengthen capacity of FSSWG on Age and Gender marker | SGFP | [12 empty] | ongoing | bar: J to D
|  | Implementation of action plan based on SGFP network workplan | Sector Chair/ SGFP | [12 empty] | ongoing | bar: J to D
| Basic Needs | Coordinate with the Basic Needs WG on the minimum expenditure baskets | Sector Chair/ All partners | [12 empty] | Not Started | bar: A; J to A; D
|  | Liaise with Basic Need WG regarding planned implementation of voucher/One Card system | FSSWG & BNWG | [12 empty] | Not Started | bar: A to A; D
| Protection | Continue coordination of FSSWG members participation at the Interagency SGBV/CP SOPs trainings to strengthen the quality and capacity response of food security partners and the referral pathways | Sector Chair/ All partners | [12 empty] | ongoing | bar: J to D
|  | Ensure members incorporate measures for PSEA in their programmes | All partners | [12 empty] | ongoing | bar: J to D
Capacity building of FSSWG members on protection mainstreaming and integration in food assistance programming and implementation
|  | Stock-taking of complaints mechanisms and investigation procedures * | Sector Chair | [12 empty] | ongoing | bar: J to D
| Livelihoods | Livelihoods and level of assistance | All partners ( FSSWG + LHH) | [12 empty] | Not Started | bar: M to A; D
| Health and Nutrition | Coordinate with the Nutrition sub-WG to promote for Comprehensive multi-sector approach to nutrition | Sector Chair/ All partners | [12 empty] | ongoing | bar: J to D
| Education | Coordinate with the Education WG ( school feeding programs). | Sector chair /All partners | [12 empty] | ongoing | bar: J to D
| JRP/JORIS | Facilitate participation of relevant ministry 2018-19 | Coordination Associate / Sector chair | [12 empty] | Not Started | bar: J to D
|  | JORIS upgrade and facilitating approvals via line ministries | All partners | [12 empty] | ongoing | bar: J to D
|  | Provide regular updates on connection and integration into JRP | Coordination Associate / Sector chair | [12 empty] | Not Started | bar: J to D
| ISWG | Strengthen collaboration and communication with other sectors by promoting Intersector Linkages | ISWG / Sector chair | [12 empty] | ongoing | bar: J to D
|  | Consolidate sector work plans to identify linkages and to providing support to Urban coordination forums as required | ISWG / Sector chair | [12 empty] | ongoing | bar: J to D
Note on C26: CRAWFORD Emma: Is this referring to FSS Gender Analysis by SGFPN?
Note on C27: CRAWFORD Emma: As for protection, we could include capacity building for partners on gender mainstreaming and integration in food assistance programming and implementation (including gender and age marker). This could be conducted by SGFPN.