## Sheet1
Thematic / Operational Area | Comment | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Winter Assistance
2017 - 2018 Interagency Winter Support Plan | distributions ended by end of March 2018 | bar: Q1 Jan to Q1 Mar
Interagency Lessons Learned Workshop | to be planned in May 2018 | bar: Q2 May
Interagency Winter Support Meeting | plan and analyse trends; define assistance packages and working modalities ahead of the 2018-2019 campaign | bar: Q2 Jun
2018 - 2019 Interagency Winter Support Plan | 2 Pager Visual | bar: Q4 Oct to Q4 Dec
Targeting - Recalibration of the Desk Formula
Tender process | joint UNHCR/WFP tender process to select the research firm that will undertake 2018 recalibration | bar: Q1 Feb to Q1 Mar
Contracting | administrative procedures finalized | bar: Q1 Mar to Q2 Apr
Preliminary findings | recalibration of the model finalized | bar: Q2 May
Communications Plan | development of communication plan in consultation with relevant stakeholders (BAWG, etc..) | bar: Q2 May to Q3 Aug
Technical Peer Review | planned by UNHCR by end of July | bar: Q3 Jul
Simulations of Technical Findings Presented | Dissemination of recalibration of technical results and implementation (e.g. BAWG, FSWG, HCT, HoHA, ISWG, etc..) | bar: Q3 Jul to Q3 Sep
Development of the Redress / Appeals Strategy | contracted research team to work on the Redress strategy | bar: Q3 Sep to Q4 Nov
Operationalization | implementation of findings and conclusion of the exercise | bar: Q4 Oct to Q4 Nov
VASyR 2018
Analysis Plan and Research Questions Developed | sector inputs | bar: Q1 Feb to Q1 Mar
Data Collection | 16 April - 4 May 2018 | bar: Q2 Apr to Q2 May
Data Cleaning + Analysis | bar: Q2 May to Q2 Jun
Preliminary findings | presentation to the sector for validation | bar: Q3 Jul
Finalization and Disseminations of Findings | final findings presented | bar: Q3 Sep
Monitoring and Evaluation Framework
Stock taking of existing activities | What types of activities BA sector partners are currently doing? | bar: Q2 Apr to Q4 Dec
Standardizing Terminology | defining outputs, outcomes, and impact monitoring | bar: Q2 May to Q4 Dec
Updating existing tools | Current harmonized tools: PDM and OM tools | bar: Q2 Jun to Q4 Dec
Exploring IS linkages | engaging with discussions with the IS WG on how to feed sector findings into the IS M&E Framework | bar: Q3 Jul to Q3 Sep
Finalize the framework and integrate into the 2019 LCRP Update | 2019 BA M&E framework | bar: Q3 Aug to Q4 Dec
Operational Areas
SOP Tool Box | Documentation of processes, procedures, and operational areas around cash based interventions, targeting, vulnerability assessments, monitoring and evaluation, etc.. And developing a tool box for sector partners. | bar: Q2 May to Q4 Dec
Communications with Communities SubWG | exploring the possibility of establishing a CWC SubWG under the Basic Assistance supplementing ongoing efforts on targeting and cash based programming. | bar: Q2 May to Q4 Dec
Revisiting the S/MEB | Engaging the sector and the intersector WG in discussions around the existing SMEB package and its current and future use. | bar: Q2 May to Q4 Dec
Thematic Discussions
Graduation Approach | the LCRP 2018 update presented a window to explore graduation approaches for vulnerable populations. This window combines efforts from the Basic Assistance, Food Security, Protection, and Livehoods sectors. Intersectoral discussions are expected to start during the second quarter of the year. Findings will inform the 2019 planning process. | bar: Q2 Jun to Q4 Dec
Social Protection and Safety Nets | Social protection is an approach currently being explored at the policy level of the LCRP. The HCT's Task Force is expected to deliver a number of statements upon which sectors will have to develop their frameworks for programmatic delivery. The Basic Assistance sector will be engaging in these discussions with relevant stakeholders as of the second quarter of the year. | bar: Q2 Jun to Q4 Dec
Protection Dividends of Cash | this is another area the sector would like to explore further. While cash assistance is being provided to economically vulnerable households under the Basic Assistance sector, using poverty estimation models, the future approach will have to have a protection lens and therefore revisiting current working modalities. discussions are expected to take place as of the third quarter of the year. | bar: Q3 Jul to Q4 Dec
LCRP 2019
2019 Update | Launch of the 2019 Planning Process | bar: Q3 Sep to Q4 Dec