## Workplan 2018
SGBV Task Force Workplan 2018
Thematic Area | Key activities/outcomes | Comments | Responsible Agencies
Prevetion of violcence | Guidance and joint interventions on how to address expolitation and risks via social media | Ongoing
Information sharing and increased safe identification and referral | Safe and ethical referrals training and ToT
Engaging with men and boys | Identification of best practices
Training/ToT on male engagement and development of tip sheets
Engaging with communities | Standardized messaging - awareness raising (including timing, methid and guidance on how to facilitate it)
Guidance/strategy/ best practices on engaging communities/community based interventions to address SGBV
Update and continue use of community leaflets (for field locations)
Services coverage and availability | 3W | Done
| Target Mapping | Done
Develop Quality assurance tool for multi-sectoral services
Case management | Capacity building: safety planning for complex cases (IPV/DM, marginalized groups ) and CM for sex trafficking, sexual exploitation, male survivors; married adolescent girls
Guidance on provision of ECA to survivors
| Trends analysis (field level, with GBVIMS actors and SGBV WG) | Ongoing
Provision of PSS | Compilation of good practices on peer to peer approach when used in GBV interventions (how to use, recommendations, safeguards)
Guidance on use of emotional support groups (when to facilitate the ESGs, how to identfy women and girls to participate in ESGs)
Access to medical services | survivor centered care (capacity building especially for CMR service providers including facilities and trained Drs) on GBV soft skills including monitoring and supervision; capacity building for social workers on CMR core concepts
Strenghten linkages between case management agencies and trained facilities to improve referals
Non specialized GBV staff trained on identification and referral to MH, how to handle MH crises, SOPs including follow up with survivors
Increase and expand awareness raising efforts with communities on access to medical services
Regular sharing of information on accessibility to CMR services (SGBV WG to CMR TF); support to the development of CMR national strategy
Assess and support (fundraising and advocacy) for MH services embedded in case management interventions
Access to Justice | Compile good practices and lessons learned and document the challenges in accessing justice and interventions recommended at the level of the SGBV TF for advocacy donors.
Produce a pager on Informed Decision for Case Managers in the context of accessing legal services (CMWG).
Develop and share a detailed referral pathway for accessing justice in the context of a GBV incident
Joint roundtables between Case Management organizations and Legal actors
Safety audits | Harmonize data collection and reporting of findings to SGBV WG (through M&E toolkit)
SGBV against children | Establish ad hoc platform joinlty with CP to: define SOPs for management of mixed/complex cases; integration of other sectors; key messages | Process launched - to be finalized
Institutional support | Guidance/checklist on handover/transferring capacities to CBO (timeframe, resources, technical skills) including modalities and recommendations for phased exit strategy
Develop a checklist of SGBV specific considerations for identification of national partners
Open SGBV coordination to specialized service providers through 1) outreach to local actors 2) mapping of local service providers 3) identification of local coordination platforms – where they exist – and inclusion of SGBV issues
Advocacy | Media; Access to Justice; Access to medical services; PSEA; donors and HCT | Ongoing
Monitoring and Evaluation | M&E toolkit - trainings for GBV organizations | 4 new trainings to be conducted in 2018
Data Analysis | GBVIMS one pager - one key issues | 3 new thematic one pager to be produced in 2018

## Implemented 2017
SGBV Task Force Workplan 2017
Action identified | Key activities/outcomes | Completed 2017 | To be implemented in 2018 | Responsible
Increase information and tool sharing among members | Create a dropbox folder to include all tools/materials developed by the TF
Guidance on basic rules to upload documents (i.e. tools to be presented to TF before, tools need to include guidance on how and when they can be used ect)
Capacity Building initiatives coordination | Reactivate online training calendar by theme
Coordinate topics/training audience
Information sharing - frontliners/other sectors | Regular update and sharing of RP on monthly basis
Safe and ethical referrals training and ToT
GBV SOPs mobile app - safe and ethical referral
Roll out 2015 IASC GBV Guidelines | Contextualization; training for selected sectors (national and field) sectoral action plans
Engaging men and boys | Desk review of already existing materials that are being used by different NGOs
Identification of best practices
Engaging with communities | Standardized messaging - awareness raising (including timing, methid and guidance on how to facilitate it)
Guidance/strategy/ best practices on engaging communities/community based interventions to address SGBV
Update and continue use of community leaflets (for field locations)
Provision of PSS | Guidance on peer to peer approach when used in GBV interventions (how to use, recommendations, safeguards)
Guidance on use of emotional support groups (when to facilitate the ESGs, how to identfy women and girls to participate in ESGs)
Case management | Guidance on self care (description of various approaches - peer to peer, coaching, psycholosgist support)
Capacity building: safety planning for complex cases (IPV/DM, Disabilities, marginalized groups )
Training materials on sex trafficking, sexual exploitation, male survivors; married adolescent girls
Guidance on supervision system
Case management | Guidance on provision of ECA to survivors
Services coverage | Hub system
| 3W |  | Done
Monitoring and Evaluation | M&E toolkit - trainings for GBV organizations |  | 4 new trainings to be conducted in 2018
Data Analysis | GBVIMS one pager - one key issues |  | 3 new thematic one pager to be produced in 2018
| Trends analysis (field level, with GBVIMS actors and SGBV WG) |  | Ongoing
Early Marriage | Establish ad hoc platform joinlty with CP to: define SOPs for management of mixed/complex cases; integration of other sectors; key messages |  | Process launched - to be finalized
Advocacy | Media; Access to Justice; Access to medical services; PSEA; donors and HCT |  | Ongoing
Access to medical services | survivor centered care (capacity building especially for CMR service providers including facilities and trained Drs) on GBV soft skills including monitoring and supervision; capacity building for social workers on CMR core concepts
Strenghten linkages between case management agencies and trained facilities to improve referals
Regular sharing of information on accessibility to CMR services (SGBV WG to CMR TF)
Institutional support | Guidance/checklist on handover/transferring capacities to CBO (timeframe, resources, technical skills) including modalities and recommendations for phased exit strategy
Develop a checklist of SGBV specific considerations for identification of national partners
Open SGBV coordination to specialized service providers through 1) outreach to local actors 2) mapping of local service providers 3) identification of local coordination platforms – where they exist – and inclusion of SGBV issues
Protection remedies for survivors | Liaise and contribute to CP assessment of shelters
Identify possivle safe alternatives to safe shelters and guidance on how to select safest options
Coordination of actors working with judiciary/law enforcement (protocols, capacity building)
Safety audits | Harmonize data collection and reporting of findings to SGBV WG (through M&E toolkit)