## Slide 1: CRS Shelter Pilot update
September 5, 2019
SSNFI WG meeting – CRS Nsambya office

## Slide 2: Background to the Shelter Pilot
To enable refugee beneficiaries to have a strong voice in the design of their own homes, the inter-agency Shelter, Settlement and Non-Food Items Working Group (SSNFI WG) wishes to move away from producing strict design drawings and bills of quantities as minimum standards for semi-permanent shelter. Selected extremely vulnerable beneficiaries should make core design decisions for their shelters and bathing areas/latrines (layout, materials etc.) with technical guidance from implementing partners to ensure eight guiding principles below are followed:
  1. There shall be no special design for vulnerable refugees; the shelters must blend in with the existing built environment and surrounding shelter typologies.
2. No provision of individual assistance at the expense of community dynamics and self-resilience. Village-level responsibility and accountability to their most vulnerable members shall be pursued.
3. There must be a harmonized prioritization for beneficiary selection within the eligible vulnerable groups.

## Slide 3: Background to the Shelter Pilot - cont’d.
4. The projects must be as environmentally sustainable as possible.
5. The projects must be as cost-effective as possible. The final range of HH unit ceiling thresholds shall be informed by the outcomes of the pilot projects and will require ongoing revisions.
6. Eliminate or minimize intermediaries by promoting local economies and peaceful coexistence through market-based approaches.
7. The projects shall seek for maximum integration with other sector initiatives and principles such as WASH, protection, environment and energy, and livelihoods.
8. The shelters must have a durability of some three to five years, be structurally safe and not pose any public health risks.

## Slide 4: Background to the Shelter Pilot - cont’d.
CRS was given 10 shelters to implement across 3 settlements of Kiryandongo, Kyangwali and Bibibidi.
Kiryandongo are having 4 pilot shelters and Kyangwali are having 2 pilot shelters.
Bidibidi was initially to pilot 4 shelters but Bidibidi been divided into 5 zones the UNHCR field team agreed to have 5 shelters instead of 4 shelters.

## Slide 5: Pilot Modality (UNHCR funds)
  Kiryandongo (4) and Kyangwali (2)
  CRS is procuring the hardware materials directly, provision of bricks is responsibility of the local crews engaged in the construction
  Payment is provided into 3 instalments: 40% for preliminaries, bricks supply and construction of walls up to the wall plate; 40% upon completion of roof, doors and windows; and 20% for finishes.
  Bidibidi (5)
  CRS is procuring the hardware materials directly for 4 shelters, provision of unburnt bricks and labour is responsibility of the beneficiary with help of local leaders or proxy, crews engaged in the construction. One Pilot Shelter is fully cash support.
  Payment for unburnt bricks and labour is provided into 2 instalments: 45% for preliminaries, bricks supply and 55% labour for completed shelter and latrine.
  Cash payment is in 3 instalments of 20% for brick supply and preliminaries, 60% for hardware materials and 20% labour for complete construction.

## Slide 6: Beneficiary Participation
  Kiryandongo and Kyangwali
  Design selection
  Understanding their roles and responsibilities in the implementation process and Signing of consent form.
  Confirmation of location of the shelter and latrine in the plot.
  support the construction crews and overall monitoring of construction works.
  Bidibidi
  Design selection
  Understanding their roles and responsibilities in the implementation process and Signing of consent form.
  Confirmation of location of the shelter and latrine in the plot.
  Seek and engage construction crews to build their our shelter
  Receive cash and pay supplied mud bricks and construction crews
  support the construction crews and overall monitoring of construction works.

## Slide 7: Type of shelter piloted
Type of shelter | Number of rooms | Where we did It | Target | Achieved
ISSB | Single room shelter:1-2 persons | Kiryandongo | 2 | 2
Mudbrick | Single room shelter: 1-2 persons | Kyangwali | 1 | 1
 | Double room shelter: 3-4 persons | Kyangwali and Kiryandongo | 2 | 2
 | Three roomed shelter: 5 and above | Kiryandongo | 1 | 1
 | 18 sq.m (3 rooms) | Bidibidi,z2 | 1 | 1
 | 14 sq.m. (2 rooms) | Bidbidi,z1,z3, z4 & z5 | 4 | 3
NOTE : in Bidibidi, there is still one pilot shelter left, it will be completed by this coming Sunday this shelter is under the full cash support modality

## Slide 8: Actual cost – using 3818.14 as exchange rate
Shelter type | Shelter size (mxm2) | How many being built as part of UNHCR pilot? | Materials | Pilot Shelter cost (BoQ) USD | Pilot Latrine cost (BoQ) USD | Bathing shelter cost* (BoQ) USD | Pilot Total cost (BoQ) USD
One-room | 3,4m x 2,8m (ex) | 2 (Kir) | ISSB + CGI sheets | 687.75 | 321.78 |  | 1010.52
One-room | 3,4m x 2,8m (ex) | 1 (Kyangwali) | Mud bricks + CGI sheets | 568.61 | 260.6 |  | 829.21
Two-room | 4,55m x 3,3m (ex) | 2 (Kyan&Kir) | Mud bricks + CGI sheets | 788.42 | 260.6 |  | 1049.42
Three-room | 5,0m x 4,55m (ex) | 1 (Kir) | Mud bricks + CGI sheets | 1014.3 | 260.6 |  | 1274.91
Two-room | 4.25m x 4m (ex) | 3 (Bidibidi) | Mud bricks + Aluzinc sheets | 674.74 |  | 138.41 | 813.14
 |  | 1 (Bidibidi) | Mud bricks + Aluzinc sheets | 674.74 | 270.27 |  | 945.01
Three-room | 5.0m x 4.0m (ex) | 1 (Bidibidi) | Mud bricks + Aluzinc sheets | 751.48 |  | 138.41 | 889.88
* Latrine without dome slab already built with support by other agencies

## Slide 9: Shelter cost analysis (excludes latrine & bath)
Shelter type | Shelter size (mxm2) | How many being built as part of UNHCR pilot? | Materials | Pilot Shelter cost (BoQ) USD | Pilot Shelter cost / sq/m. USD/SQ.M
One-room | 3,4m x 2,8m (ex) | 2 (Kir) | ISSB + CGI sheets | 687.75 | 72.35
One-room | 3,4m x 2,8m (ex) | 1 (Kyangwali) | Mud bricks + CGI sheets | 568.61 | 59.73
Two-room | 4,55m x 3,3m (ex) | 2 (Kyan&Kir) | Mud bricks + CGI sheets | 788.42 | 52.51
Three-room | 5,0m x 4,55m (ex) | 1 (Kir) | Mud bricks + CGI sheets | 1014.3 | 44.58
Two-room | 4.25m x 4m (ex) | 3 (Bidibidi) | Mud bricks + Aluzinc sheets | 674.74 | 36.69
 |  | 1 (Bidibidi) | Mud bricks + Aluzinc sheets | 674.74 | 36.69
Three-room | 5.0m x 4.0m (ex) | 1 (Bidibidi) | Mud bricks + Aluzinc sheets | 751.48 | 37.57
* Latrine without dome slab already built with support by other agencies

## Slide 10: Shelter cost distribution (material’s – labor)
Bidibidi_18sq.m_unburnt brick_roofing sheets | Bidibidi_14sq.m_unburnt brick_roofing sheets

## Slide 11: Shelter cost distribution (material’s – labor cost)
Kiryandongo_3 rooms_unburnt brick_roofing sheets | Kiryandongo_1 room_ISSB_roofing sheets

## Slide 12: Challenges
Kiryandongo & Kyangwali | Bidibidi
Initial Bills of Quantities were under estimated Shortage of materials and delay Drawings were not detailed enough Roof first strategy in Kyangwali challenging to implement Hard to find dome-shaped slab: CRS has not found trained local sanitation artisans to make these slabs. Challenging to advocate able household beneficiaries to have a free contribution to Challenging to conduct Beneficiary registration especially in Kyangwali. Heavy rainfall affected pilot shelter constructions. | Labour and local cost of shelter construction from the previous projects might not reduce easily. Limited management and Negotiation skill of beneficiaries. Peaceful coexistence may diminish since beneficiaries select people they know and within the settlement. Beneficiary change of mind from cash modality. Cost of shelter increases during rainy season (increase tarpaulin, loss of bricks) Inadequate source of manufactured materials and timber within the settlements. Limited knowledge on construction works by un-able beneficiaries make monitoring shelter works hard.

## Slide 13: Recommendations
1. Technical and design
CRS technical teams to seek OPM/UNCHR approval to use of burnt bricks for latrine plinth walling as some soil conditions in Kyangwali and Kiryandongo are too soft.
A shelter construction and maintenance manual should be provided to each beneficiary and construction crew during handover of site to ensure that shelters are built according to expected technical standards.
Technical teams should closely monitor construction crews to ensure timely corrective of snags on shelters under construction.
The technical teams to review and harmonize the designs, bills of quantities for Kyangwali and Kiryandongo to address the variation in shelters dimensions, height, windows and size. The following specifications were agreed as way forward: Wall plate height of 2.2m, hence adjust the drawings to 2m to the lintel and additional 2 block courses on the lintel before the wall plate (making it about 2200mm to the wall plate). This will make the shelters to relatively match in terms of height with the surrounding shelters.
Timber reinforcement at the corner of the wall plate to make it work as tie beam.
Window shutters size reduced to 650mmX1000mm, as beneficiaries are not comfortable with our current window size which is too wide.
Piers at all corners or thickening of walls at gable side to increase structural safety.
Plinth wall built in header bond and superstructure on stretcher bond.
Pitch angle of 30 degrees for the three-room shelter, 28 degrees for the two-room shelter and 25 degrees for the single room shelter.

## Slide 14: Recommendations cont’d.
2. Beneficiaries’ engagement
Early involvement of the refugee leaders, protection actors and community members in targeting, planning, implementing and monitoring of activities to enhance ownership and increase speed of implementation.
Community mobilization teams to better sensitize beneficiaries regarding providing free of cost contribution towards construction of shelter.
3. Operations
Pickup is needed for the Kyangwali office that will assist in transporting construction materials.
Joint assessment and technical working group verification of works to ensure compliance with standards.
The best timing for construction and supervision of mudbrick shelter construction activities is in the dry season.
One day’s workshop shop should be conducted with construction crews and households to explain their duties and responsibilities during the shelter construction including explaining construction process, the timelines and contractual obligations.
LPO for shelter and latrine will be separated to allow payments even in case shelter and latrine go at a different speed.
Allowances for small variations depending on the site.
Insert a clause for tarps liability (on loan) in the contract.
During scale up of shelter construction, the technical and procurement teams should identify additional construction crews and allocate work according to quality of their works and speed of construction, including implementing the clause on one percentage penalty on delayed completion.
A construction crew to comprise a comprises minimum of 9 members four skilled (three masons and carpenter) and five helpers in-order have both shelter and latrine construction happening concurrently.

## Slide 15: ISSB – One-room shelter and latrine/bathing area in Kiryandongo

## Slide 16: Mud brick – One-room shelters in Kiryandongo and Kyangwali

## Slide 17: Shelter construction Stages K & K

## Slide 18: Kyangwali – Roof being built first to prevent rain/wind damage

## Slide 19: Shelter construction Stages _Bidibidi

## Slide 20: Bidibidi – 3 rooms -18sq.m. Unbrick Shelter

## Slide 21: Thank you for listening