**Youth Taskforce (YTF) Minutes of Meeting**

Tuesday, 5 Nov 2019

Location: UNFPA/QS Youth Center

Time: 10.30 - 11.35

**Attendees:**

Bothaina (UNFPA), Dine (NRC), Manar and Wijdan (Blumont), Nadeen (IFH), Hanan (QS), Sara(RI), Laith, Reema and Sylivia (UNICEF), Islam and AymanKhaldi (LWF), Asma Tawalbeh (JHAS), Mustafa (MC)

|  |  |  |
| --- | --- | --- |
| **Agenda Item** | **Discussion** | **Action Point** |
| Following-up on the previous MoM action points | * YTF/SGBV joint workshop action points. Updates were shared on the progress of Action Points.
* YTF and RH Sub-Working group joint work under the Compact was discussed.
* Hani UNHCR did not attend to present the REF-GIS. This will be postponed to next meeting
* YTF - CBR Committee will be Ms. Wijdan from RI

 | * UNFPA to arrange with GBV team an oreintation session on Sexual Harassment
* A session on ASRH and Compact is postponed to end of Nov with the RH Sub-Working group.
* Hani UNHCR and Dina NRC will provide a brief PPT on REF - GIS next YTF meeting. Hani will provide an update by November on the System.
* Reema UNICEF will provide an update on the “Youth Services pathway” once updated.
 |
| 2020 YTF Planning Workshop  | * Date of the workshop is the 11th of November. The draft agenda was discussed with attendance. Comments includes:
* Making sure the policy paper recommendations are addressed in the workshop
* Share briefs about the COMPACT prior to the workshop
* LWF suggested exploring Syrian Club committee as a potential youth engagement platform with YTF
 | * YTF Chair to send bilateral emails to YTF members who require their management approval to attend the workshop.
* Chair to share briefs about the COMPACT prior to the workshop
* Extend the deadline for registration in the workshop till Thursday
 |
| 16 Days of Activism Campaign - YTF Joint activity  | A workshop was conducted on the 29th of Oct to follow on the 16 Days of Activism Campaign - YTF Joint activity. An email was shared with a plan and bilateral follow ups are conducted. Updates: The movie. Blumont is leading the work on it. Success stories are being collected. Filming will take place next week. UNICEF will be arranging Village 5 shooting and share the segment with Blumont The film will be presented on the celebration day, and remain available for organizations or/and cinema to show it. Messaging: Messages were shared from the SGBV working group The BazarSara presented the proposed table to organize selling items on the day. Production of new materials should be finalized by 21st of Nov Printing for promotional materials UNFPA Can support printing if materials are provided three week prior the needed dates. Grafiti QS + Blumont are working on this by working with Syrian artists and discussing the general theme. They will produce 10 paintings that will be previewed and one graffiti will be developed on the spot.Platform for discussion This station aims to explain what the campaign is about by engaging with Syrian volunteers. A Screen that plays the key messages will be added. Theater Skkitch IFH will confirm this by Thursday Livelihoods WG - Islam as a co-chair shared they are intrested to join the campagin. The WG are planning a Bazar outside the camp from 27- 29 Nov. An email will be shared with more details for organizations interested in participating.   | * 2 December is the set date for joint YTF 16 Days of Activism Campaign activity. Location will be at Blumont center
* Checking on the location should be done be engaged organizations before the 19th
* YTF members to share success stories to Blumont by 7th of Nov. Please share Names + stories + contacts.
* Blumont will present the films in the next YTF meeting for feedback.
* Next updates about the work progress to be on the agenda of the next YTF meeting
* YTF members to share inputs on the bazar Matrix by 7th of Nov
* By the 19th the promotional and communication plan should be finalized.
* Dina to organize with Esraa an orientation session for Syrian volunteers to speak about the theme
* YTF members to share names of Syrian volunteers.
* Bothaina to follow up on needed printed promotional materials.
* IFH to confirm the theater skitch by 7th of Nov
 |
| Review the YTF FP's for working groups. | An update was shared based on YTF members contribution . For the remaining sectors Asma Tawalbeh/JHAS volunteered for Health, Hanan/QS for MHPSS, and Sara/RI for education . WASH remains with no FP’s

|  |  |
| --- | --- |
| ***Working Group / Task Force*** | ***YTF Member FP*** |
| *WASH* |  |
| *Protection* | *Nadeen IFH and Manar Blumont* |
| *Basic Needs and Livelihoods* | *Reema and Sylvia/UNICEF* |
| *Health* | *Dr. Ghada and Ms. Asma Tawalbeh JHAS* |
| *Reproductive Health* | *Dr. Ghada/ JHAS* |
| *Education* | *Sara Halawani/RI* |
| *MHPSS* | *Hanan/ Questscope* |
| *CP and SGBV* | *Yazan/ SC* |
| *Community Mobilization* | *Hani/UNHCR* |
| *Age and Disability* | *Wijdan/ RI* |
| *Security* |  |
| *CMC* | *Bothaina/UNFPA* |
|  |  |

 | * Chair to share with CMC the new FP’s and extend an invitation for the workshop to discuss FP’s role and responsibilities
 |
| Updates from member organizations and AoB | * QS announced Y-PEER upcoming refresher training. More details will be shared in email
* QS announced Breast Cancer Awareness Day on the 10th of Nov at 11.00 am at UNFPA/QS Youth center
 |  |
| Next Meeting 19th of November. Location TBD.  |