# RESPONSE MONITORING TASK FORCE – MEETING 3

| # Minutes | November 22, 2018 | 15:00-16:00 | CONFERENCE ROOM |
| --- | --- | --- | --- |

| ### Meeting called by | BO HURKMANS – IM TEAM LEADER |
| --- | --- |
| ### Type of meeting | COORDINATION |
| ### Facilitator | BO HURKMANS |
| ### Note taker | HILLARY MUMBERE |
| ### Attendees | BO HURKMANS (UNHCR), HILLARY MUMBERE (UNHCR), DAMJAN NIKOLOVSKI (UNHCR), JOHN BERNARD (ARC), REBECKA RYDBERG (REACH) |

## Agenda topics, 	Introduction, Review of action points from last meeting / task force work plan, Review of progress on indicators and standardising activities, Review of standard procedure for reporting, AOB

| ### discussion |  |  |  |
| --- | --- | --- | --- |
| - Review of action points from last meeting / task force work plan - Platform identification to be validated at regional meeting in Nairobi on 10-11 December, as a result ActivityInfo might be used in other RRRP countries too. - Dashboard templates can be produced with REACH support up to end of December (due to length of PPA). - Reporting process and monitoring framework should be validated by mid-January for those sectors that will report activities on a monthly basis (i.e. start using the platform in February). - Review of indicators and standardising activities - Meetings have been held so far with Shelter, Settlement and NFI, Environment and Energy, Livelihoods, Education, Protection and Food Assistance. - Meetings are still outstanding for Health and WASH. - A monitoring framework that pulls together RRP objectives, indicators, targets and links them to sector activities was presented for feedback and will be shared along with the minutes. - Review of standard procedure for reporting - There was a need to compress the timeline for reporting and to differentiate between RRP reporting and activity reporting, a revised procedure has therefore been developed. Timeline: Roles and responsibilities for activity reporting: Roles and responsibilities for RRP reporting: - AOB - Next meeting will be on 6th Dec (3 – 4pm) |  |  |  |
| ### Action items |  | ### responsible | ### Deadline |
| Reach out to colleagues in UBOS, NPA and UNDP |  | BO | EoY |