| Name | Evictions / Litani TF | Meeting Date | 20 May 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 14:30 |
| Co-Chairs | Hussein Salem (MoSA) – Josep Zapater (UNHCR) | Meeting Duration | 2:00 hour |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |
| Purpose of Meeting | Review current situation and agree on next steps on the Litani and solid structures situation |

Meeting

Meeting agenda

- Updates on the Litani situation

- Solid structures situation:

  - Key figures and results of the field assessment in Arsal

  - General approach and main conclusions from the situation on the ground

  - Next steps

Discussions – Litani situation

MOSA updated on current discussions ongoing in Beirut between the different ministries and inquired about data still necessary from the field. A question was asked as regards the surface available per family in the relocation sites. MOSA clarified that a third site has been identified, and that it can also be considered as a relocation site if more space is needed.

Action points – Litani situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Share with MOSA Beirut technical data as requested | UNHCR | 21 May |  |
| Conduct a first assessment of the third site available | Shelter sector | 22 May |  |

Discussions – Solid structures situation

UNHCR explained the importance of measuring humanitarian’s ability to intervene on the basis of facts on the ground (i.e. the result of assessments). They will also depend on the rhythm at which dismantlement / destruction will happen on the ground. Desk data (IAMP, in particular), as well as results of field assessments, yield also clear conclusions on how the operation needs to happen on the side of authorities, so as to minimize the humanitarian impact on the refugees as well as to enable humanitarians to rebuild.

After a presentation of the result of IAMP data, as well as field assessments, a few quick conclusions were presented on the above, among other:

- Deadlines, as well as the rhythm at which dismantlement / demolition happens, need to be reasonable and adaptable to humanitarians’ ability to intervene,

- In Arsal, many structures will necessitate skilled labour as well as heavy machinery for dismantling / demolition,

- In most cases, refugees will need to be temporarily relocated to enable dismantling / demolition, as well as building of new structures.

It was also decided that the Arsal situation will be coordinated from Arsal, with participation, as appropriate, of the Municipality and local NGOs.

Action points – Solid structures situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Humanitarians will share with authorities minimum requested operational modalities / advocacy points, in order to minimize impact on refugee populations as well as enable humanitarians to rebuild | All | ASAP |  |
| Authorities to share the above with LAF | To be determined | ASAP |  |
| Protection Core Group meeting on messaging to refugees | Protection | Tuesday 21 May |  |
| Technical meeting to evaluate stocks and geographical responsibilities | UNHCR | Wednesday 22 May in UNHCR Zahle |  |
| Coordination meeting in Arsal for joint updates between local and INGOs and decide on actions and respective responsibilities | UNHCR | Thursday 24 May 11:00 in Arsal |  |

Next meeting

- To be determined.

# Text boxes

Evictions / Litani  TF – Minutes of Meeting