| Name | Intersector / ETF | Meeting Date | 9 January 2019 |
| --- | --- | --- | --- |
| Meeting Location | UNHCR Zahle Sub-Office | Meeting Time | 13.00 |
| Co-Chairs | Hussein Salem (MOSA), Josep Zapater (UNHCR) | Meeting Duration | 2 hour |
| Minutes Prepared by | Josep Zapater (UNHCR) |  |
| Purpose of Meeting | Regular Intersector coordination / ETF meeting on storms |

Meeting

Meeting agenda

- Updates: regional & country situation, return movements.

- Current situation in Lebanon.

- Storm situation: follow up on action points from last meeting (attached), as well as review of current situation and next steps.

- Litani river situation.

- AOB.

Discussions

- MOSA, UNHCR and UNDP, among other, updated on the current situation affecting vulnerable and ordinary Lebanese, as well as measures of assistance, coordination and communication. There is wide consensus that the Intersector, sectors and its members need to upgrade and systematize its assistance to host communities, both at the community and at the household level, and communicate publicly about it.

- UNHCR updated on recent refugee returns to Syria.

- An update and a discussion ensued on the storm situation and usage of RNA.

- MOSA updated on the approval of relocation of site 014 next to the Litani river and next steps. Delegate underlined the difficulty of relocate during rains or while soil is still wet. It was agreed however to commence the process as soon as Governor notifies ISF.

- UNHCR updated on the first draft of the post-dismantlement study in Arsal, and of the intention by the Intersector coordination to foster more coordinated assessments in order to feed advocacy and assistance.

Action points – Current situation in Lebanon

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Organize a meeting with the main active agencies assisting Lebanese, to explore targeting, coordination and communication. Meeting will also serve to prepare the 23th of January meeting with the Governor of the Bekaa. | Interagency team | Week of 13th January |  |
| Organize a dedicated meeting in Arsal | Interagency team | ASAP |  |

Action points – Storm situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Adapt Emergency SOPs to clarify the criteria for RNA triggering – to ensure that it is used when useful, but also to avoid overreporting and over coordination. | UNHCR | ASAP |  |
| Organize a lessons learnt on the use of RNA | UNHCR | ASAP |  |
| Update list of relocation sites, taking into account changes in Yasmine and Aude sites | MOSA and UNHCR | ASAP |  |
| Follow up on approvals for Yasmine and Aude sites as contingency sites – to ensure Governor writes to MOIM in Beirut and MOIM approves the use of sites for contingency, on the basis of the letter addressed by URDA to the Governor of the Bekaa through MOIM | MOIM | ASAP |  |

Action points – Litani situation

| Action needed | Focal point | Deadline | Status |
| --- | --- | --- | --- |
| Request ISF to notify families at 014 site | Governor – MOIM for follow up | ASAP |  |
| Implement all action points agreed upon on 7th of October Litani Task Force meeting (attached) | All – as per minutes on 7th of October Litani Task Force meeting | Right after the step above |  |

9 January 2020

# Text boxes

TF – Minutes of Meeting