## Sheet1
Coordination workshop Bekaa - coordination action plan
Not started
Ongoing
Parked until capacities are identified
Finished
Issues arising from the coordination workshop |  | Priority | Focal points | Timeline |  | Status | Status | Observations
Coordination practice
| Distribution lists, timeliness of invitations and minutes | 1 | IS team (Josep, Hussein, Mohammed). Jamal for distribution lists |  |  |  |  | UNHCR will have one more coordination staff in June. UNDP has nominated its coordination staff
| Agencies commit to send staff with the right seniority | 1 | All
Coordination formalization
| TOR Intersector | 1 | Small working group
| TOR Interagency | 2 | Small working group
| Increase electronic communications inside Interagency | 1
| Develop intersector strategy and action plan | 1
| Lessons learnt / formalize MSA | 2 | Paul
Strengthen knowledge management
| Reinforce knowledge, information and analysis management capacities in the Bekaa in order to: Improve evidence-based decision making on coverage of gaps and priorities, Improve information to authorities on humanitarian activities, in Arabic, Facilitate more electronic-based sharing of information among Interagency, Strengthen knowledge and analysis of the situation in the Bekaa. | 1 | IS team |  |  |  |  | UNHCR is seeking additional funding for IM personnel. Other UN agencies and personnel are invited to seek additional funding or pool resources, once there is a workplan of the Intersector
Contingency planning
| Complete contingency planning | 1 | Bobbie, Hussein
Substantive issues
| Vulnerability | 1
| ITS management | 3 | [5 empty] | Needs to wait until after elections. Needs national discussion.
| Communication with communities | 1
| Peaceful coexistence | 1 | Mohammed, Paul, Hussein