## IS-Coordination
2022 LCRP Shelter Sector Workplan - Sector Coordination / Inter-Sector priorities
2022 Timeline
Link to IS Priority/Mainstreaming Area Or link to IS priority | Key Priorities | Main Actions | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners (optional) | Additional Comments | Status
Coordination | Sector Coordination Efforts | Maintain coordination and communication with the Housing Sector under the 3RF | X | X | X | X | LCRP Shelter Sector Coordinators
|  | Support the analyis of the MSNA data and discuss the revision of the targeting of vulnerable Lebanese | X | X |  |  | LCRP Shelter Sector Coordinators + Core Group
|  | Update the service mapping and referral monitoring. | X | X | X | X | LCRP Shelter Sector Coordinators
|  | Maitain a drop box folder to include all Guidance and tools/materials to SWG. | X | X | X | X | LCRP Shelter Sector Coordinators
|  | Ensure cross attendance and participation in the other sector's working groups and provide important Shelter sector updates. | X | X | X | X | LCRP Shelter Sector Coordinators
|  | Update the Minor Repair in non-residential buildings technical guidelines | X | X |  |  | Minor Repair Temporary Technical Committee + Core Group
|  | Update the Weatherproofing in informal settlements technical guidelines | X | X |  |  | WP Temporary Technical Committee + Core Group
|  | Finalize and endorse the Cash for Rent technical guidelines | X | X |  |  | CfR Temporary Technical Committee + Core Group
|  | Finalize and endorse the Area-based Approach technical guidelines | X | X | X |  | ABA Temporary Technical Committee + Core Group + Intersector
|  | Finalize and endorse the Upgrading of residential buildings technical guidelines | X | X |  |  | Upgrading of residential buildings Temporary Technical Committee + Core Group
|  | Finalize and endorse the Housing-Land and Property (HLP) technical guidelines | X | X |  |  | HLP Temporary Technical Committee + Core Group + LAWG
|  | Develop methodology to set a baseline and regularly update the CfR transfer value | X | X | X | X | LCRP Shelter Sector Coordinators + Field coordinator
|  | Develop guidelines on minimum standards to produce and report multi-sectoral area/ neighborhood profiles | X | X |  |  | LCRP Shelter Sector Coordinators + UNHabitat + NRC + Intersector
|  | Finalize and endorse, in coordination with the Protection/SOST sectors, the cross-sector response guidance document to evictions and strengthen the community level eviction guidance. | X | X |  |  | LCRP Shelter Sector Coordinators + Protection Mainstreaming Lead
|  | Develop a protocol for referring structurally unsound buildings | X | X |  |  | LCRP Shelter Sector Coordinators + UNHabitat
|  | Update and launch the Collective Site Mapping Assessment (COSIMA) | X | X | X | X | LCRP Shelter Sector Coordinators + Field coordinator
| Sector Advocacy Efforts | Joint advocacy between the Shelter and the Protection sector to increase funding for cash for rent as a mean to respond to and mitigate eviction. | X | X | X | X | LCRP Shelter Sector Coordinators + Protection Sector Coordinators
|  | Advocate to increase funding for urban shelter intervetions where almost 70% of the refugee population lives with more than half living in substandard shelter conditions. (Both BML and North have a low number of active shelter partners with some areas completely uncovered in 2022) | X | X | X | X | LCRP Shelter Sector Coordinators
|  | Advocate for the adoption of the ABA by the Intersector | X | X | X |  | LCRP Shelter Sector Coordinators
| Inter-Sector Coordination | Ensure regular information flow to and from IS/IA at national and regional level | X | X | X | X | LCRP Shelter Sector Coordinators
|  | Any activity as identified in the IS workplan | X | X | X | X | LCRP Shelter Sector Coordinators
|  | Engage in Inter-Agency discussions related to operationalisation of dollarisation in terms of monitoring the impact and risks on the community and regularly evaluating cash for rent program through the year. | X | X | X | X | LCRP Shelter Sector Coordinators
IS Joint Priority | Sector Situation Analysis | Update the funding and needs mapping per governorate | X |  | X |  | LCRP Shelter Sector Coordinators
|  | Update and issue the needs and gaps analysis in residential and non-residential buildings - VASyR |  |  | X |  | LCRP Shelter Sector Coordinators
| Reporting | Keep ActivityInfo reporting updated | X | X | X | X | LCRP Shelter Sector Coordinators and IM
|  | Keep the Inter-Sector service mapping updated | X | X | X | X
|  | Produce quarterly reporting dashboards | X | X | X | X
|  | Update the interactive dashboards | X | X | X | X
| Accoutability to affected population | Promote the review and adoption of the Inter-Agency Minimum Standards on Complaints and Feedback Mechanisms | X | X | X | X | LCRP Shelter Sector Coordinators
Mainstreaming | Protection | Collaborate with the Protection sector to integrate guidance on community consultations with representation from all groups within settlements/ shelters | X | X |  |  | LCRP Shelter Sector Coordinators
|  | Develop/ organize a national level protection training for shelter partners on safe identification and referral of protection cases by field staff. | X | X |  |  | LCRP Protection Sector Coordinators
|  | Work closely with protection and BA sector to monitor the risks and impact related to cash for rent activities. | X | X | X | X | LCRP Shelter Sector Coordinators
| Environment | Collaborate and coordinate with the inter-sectoral Environmental Task Force (ETF) based at the Ministry of Environment to mainstream environmental considerations and seek their guidance on environmental policies, application of the environmental marker guide, and ensuring the response to all complaints that may rise. | X | X | X | X | LCRP Shelter Sector Coordinators
Implement relevant trainings, namely on C&D waste management, Solid Waste Management
|  | Coordinate with ETF and SW Task Force at MoE on the disposal of shelter material, from IS to final disposal site and put in place relevant reporting mechanism | X | X | X | X | LCRP Shelter Sector Coordinators
| Gender and SGBV | Gender in Humanitarian action training is conducted in 2022 at national and regional level |  | X | X | X | Coordinator and Gender Specialist
|  | Gender analysis two pager is drafted with support from Interagency Gender Specialist |  | X |  |  | Gender/SGBV FP, Coordinator and Gender Specialist
|  | All SHELTER assessments include gender specific questions and gender analysis. Gender analysis is part of the reports on shelter needs in Lebanon (SRF) | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Nomination of gender and SGBV Focal point of the sector | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Feedback mechanisms involve at least 50% of women and girls | X | X | X | X | Gender/SGBV FP and Coordinator
|  | Analyse disaggregated sector results on a quarterly basis and adapt activities to address gender inequalities | X | X | X | X | Coordinator and Gender Specialist
|  | Initiate a reflection on how to support FHH in informal settlements |  | X | X | X | Coordinator and Gender Specialist
|  | Initiate a reflection on how to provide cash for rent to FHH or women and girls to prevent and mitigate exploitation, including sexual exploitation |  | X | X | X | Coordinator and Gender Specialist
|  | SGBV risk mitigation analysis and mitigation measures in place in cooperation with the SGBV Risk Mitigation Committee (SGBV TF) |  | X | X | X | Coordinator and SGBV Risk Mitigation Committee (SGBV TF)
|  | Organise a meeting to present results of the mapping of women's organisations and how to engage them for assessments and implementation |  |  | X |  | Coordinator and Gender Specialist
| Conflict Sensitivity | Quarterly updates on the Tensions Landscape at Shelter Working Groups Thematic discussions with Conflict Sensitivity focal point Training partners on conflict sensitivity | X | X | X | X | LCRP Health Sector Coordinator & CS Mainstreaming Focal Point
Note on B4: Comment: Reviewed by PM all sound.

## Logframe Activities
2022 LCRP Shelter Sector Workplan - Logframe Activities
2022 Timeline
Sector Output | Key Activities | Q1 | Q2 | Q3 | Q4 | Responsible | Main Partners | Additional Comments | Statute
Outcome 1: Reduce immediate protection-related shelter needs of most vulnerable households.
Output 1.1: Temporary shelters (informal settlements and non-residential buildings) and residential shelters (for protection/referral cases) hosting vulnerable displaced populations are maintained at livable and safe conditions | Activity 1.1.1: Weatherproofing of substandard non-residential buildings. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead | UNHCR, Medair, SCI, Concern, Intersos, Solidarites
| Activity 1.1.2: Minor repair of substandard residential and non-residential buildings. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 1.1.3: Upgrading of substandard residential shelters to meet minimum/humanitarian standards [for referral/protection cases]. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 1.1.5: Weatherproofing and maintenance of makeshift shelters within informal settlements. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 1.1.6: Providing conditional Cash for Rent in residential buildings. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 1.1.7: Providing temporary shelters within structured temporary settlement, in coordination with the GoL. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 1.1.8: Providing site improvements of informal settlements. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 1.1.9: Providing fire risk mitigation in informal settlements and in substandard residential and non-residential buildings through awareness sessions, firefighting training sessions and firefighting kit distribution. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 1.1.10: Awareness-raising on proper disposal of damaged non-reuseable shelter materials in informal settlements. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
Outcome 2: Improve access to adequate shelter in disadvantaged areas for enhanced stability
Output 2.1: Residential shelters for vulnerable communities in disadvantaged areas are upgraded | Activity 2.1.1. Upgrading of substandard residential shelters to minimum standards as part of a single-sector approach; | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 2.1.2. Upgrading of substandard residential shelters to minimum standards as part of a multi-sectoral approach; | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 2.2.3: Stabilizing residential shelters with compromised structural/architectural elements (this includes a temporary relocation component targeting families affected by the stabilization work); | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 2.2.4. Upgrading of common areas within substandard residential buildings and non-residential buildings. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
Output 2.2 Multi-sectoral assessments are produced for areas of vulnerable populations to facilitate sectorally integrated response | Activity 2.2.1: Assessing/profiling vulnerable geographic areas to contribute to sectorally integrated responses in areas with vulnerable populations. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead | NRC, UNHabitat
Outcome 3: Enhance the contribution of national institutions and organizations to the housing situation in Lebanon.
Output 3.1 Capacity building support to national organizations and institutions contributing to shelter and housing situation in Lebanon | Activity 3.1.1: Capacity building of national institutions and organizations on shelter response. | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead
| Activity 3.1.2: Production of shelter and housing-related studies and reports that are made accessible and widely disseminated and include a strong gender analysis | X | X | X | X | Shelter Sector Lead (MoSA) & UNHCR co-lead + 3RF + Gender Specialist